## UserStories
ID | Work Item Type | Title | Description | Task Type1 | MoM updated and attached | Action items identified and Tasks created | Related Feature identified and linked in ADO | SOW Annexure ID identified | Annexure ID1 | Data Migration needs identified and Tasks created | Area Path | Start Date | Acceptance Criteria | Fit Gap Status | EPIC ID | FEATURE ID | WORKSHOP ID
| Workshop | 01. Sales - CE Record to Report UST Led Workshop - 28/Sep/2026 | Business process workshop to validate and align on how the partner life cycle process will operate across Zinfi (PRM platform) and Dynamics 365 CE: partner onboarding, account planning, lead and opportunity management, deal registration, partner visibility, contracting, quotation and discount approval, order capture and fulfillment status, install base, service entitlements, and training/case management hand-offs. Key decisions recorded: partner records sync from Zinfi to CRM after onboarding is finalized and are read-only in CRM; one partner maps to one legal entity; leads are primarily created in CRM by Heartstream and distributed to partners; opportunity pipeline is global for phase 1; install base is preferably created on delivery. Downstream impacts: BRD/SDD updates, test cases and test data requirements to be derived from the approved stories. Business process alignment only; detailed design/solution deferred to subsequent fit-gap and solutioning sessions. | [7 empty] | Day 2\CRM | 28-09-2026 08:00
67461 | Epic | 01. B2B Direct Sales | [12 empty] | 67461
67462 | Epic | 02. B2B Direct Through Reseller | [12 empty] | 67462
67557 | Epic | 03. B2B Direct Service & Solution Delivery | [12 empty] | 67557
67572 | Epic | 04. Service Support | [12 empty] | 67572
67488 | Feature | 3. Lead Assessment | Input: Marketing Qualified Leads (MQLs) Activities : 3.1 Generate Leads 3.2 Score & Qualify Leads 3.3 Identify MQLs Output: Qualified Sales Leads | [11 empty] | 67461 | 67488
67489 | Feature | 4. Opportunity Management | Input: Sales Accepted Leads Activities : 4.1 Create Opportunities 4.2 Manage Sales Pipeline 4.3 Track Sales Activities 4.4 Identify Upsell/Cross-Sell Opportunities 4.5 Manage Sales Forecast / Forecast Categories/ Win Lost Analysis 4.6 Review Sales Analytics & Forecast Reports Output: Qualified Sales Opportunities | [11 empty] | 67461 | 67489
67492 | Feature | 7. Quotation & Pricing | Input: Customer Needs Activities : 7.1 Create Quotations 7.2 Add Products, Services, SaaS /Subscriptions as applicable 7.3 Define Payment / Invoicing Terms 7.4 Negotiate & Revise Quote 7.5 Share with Customer for Approval Output: Customer Decision Stage | [11 empty] | 67461 | 67492
67506 | Feature | 2. Partner Onboarding & Qualification | Input: Partner Program Framework & Channel Policies Activities : 2.1 Capture Partner Applications 2.2 Evaluate Partner Eligibility 2.3 Approve Partner Enrollment Output: Approved Partner Profile | [11 empty] | 67462 | 67506
67507 | Feature | 3. Partner Contracting & Commercial Setup | Input: Partner Program Framework & Channel Policies Activities : 3.1 Create Partner Account 3.2 Define Partner Pricing & Discounts 3.3 Define Rebate Eligibility & Rules 3.4 Establish Partner Agreements Output: Active Partner Contract &Commercial Terms | [11 empty] | 67462 | 67507
67508 | Feature | 4. Commercial Terms Synchronization | Input: F&O Commercial Setup Activities : 4.1 Sync Pricing & Discounts 4.2 Sync Rebate Structure Output: Updated Partner Commercial Data in Zinfi | [11 empty] | 67462 | 67508
67510 | Feature | 6. Partner Data Available in CRM & synchronization with FnO | Input: Partner Data Synced from PRM Activities : 6.1 Partner Data Availability in CRM 6.2 Partner Data (Status/Health/Score/Training /complaince / engagement /trends) made avaialable 6.3 Sync Partner Data with F&O Output: Partner Data Available in. D365 CE Input: Active Partner Account in CE Activities : B.1 Sync Partner Profile with F&O B.2 Sync Partner Account Information with F&O Output: Partner Data Available in D365 F&O | [11 empty] | 67462 | 67510
67512 | Feature | 7. Partner Training & Enablement | Input: Active Partner Account & Portal Access Activities :7 .1 Provide Partner Training 7.2 Deliver Certification Programs 7.3 Share Sales & Marketing Content 7.4 Track Training Completion Output: Enabled & Certified Partner Network | [11 empty] | 67462 | 67512
67514 | Feature | 9. Partner Lead Generation & Performance | Input: Partner-Generated Leads & Campaign Engagement Data Activities : 9.1 Generate Partner-Sourced Leads 9.2 Track Campaign Performance 9.3 Measure Lead Generation Outcomes Output: Qualified Partner-Sourced Leads | [11 empty] | 67462 | 67514
67515 | Feature | 10. Lead Registration & Qualification | Input: Qualified Partner-Sourced Leads Activities : 1.1 Register Partner-Generated Leads 1.2 Validate & Qualify Leads 1.3 Assign or approve lead ownership Output: Qualified Partner Leads | [11 empty] | 67462 | 67515
67516 | Feature | 11. Opportunity Management | Input: Qualified Partner Leads Activities : 2.1 Create & Manage Opportunities 2.2 Track Opportunity Progression 2.3 Manage Partner & Sales Collaboration Output: Qualified & Sales Opportunity | [11 empty] | 67462 | 67516
67517 | Feature | 12. Quotation & Pricing | Input: Qualified Sales Opportunities Activities : 3.1 Create Quotations 3.2 Apply Partner Pricing & Discounts & Promos & Start - End Date 3.3 Define Commercial Terms 3.4 Negotiate & Revise Quotations 3.5 Obtain Customer Sign-off Output: Customer Decision for Quote | [11 empty] | 67462 | 67517
67519 | Feature | 14. Commercial Pricing Management | Input: Product Catalog & Pricing Policies Activities : 5.1 Maintain Trade Agreement 5.2 Manage Cust Groups 5.3 Maintain Pricing Discounts 5.4 Maintain Promos Output: Customer-Specific Pricing & Discount Rules | [11 empty] | 67462 | 67519
67521 | Feature | 16. Order Capture / Management & Order processing by order sync between F&O and CRM | Order Capturing Input: Active Customer Contract & Commercial Terms Activities :8.1 Create Customer Order8.2 Validate Pricing & Entitlements8.3 Submit Order Output: Submitted Customer Order <b>Order Processing</b> Input: Submitted Customer OrderActivities :A.1 Synchronize Order to Commerce HQ Output: Order Synced with Commerce HQ | [11 empty] | 67462 | 67521
67522 | Feature | 17. Sales Order Approval | Input: Validated & Submit Sales Order for fulfillment Activities : 12.1 Validate Sales Order 12.2 Confirm Sales Order 12.3 Submit Sales Order for fulfillment Output: Confirmed Sales Order Ready for Fulfilment | [11 empty] | 67462 | 67522
67523 | Feature | 18. Fulfillment & Shipment | Input: Order Released for Fulfillment Activities : 14.1Process Fulfilment & Shipment 14.2Update Shipment Status 14.3Notify Partner / Customer 14.4Update Order Status Output: Fulfilled Order & Delivery Confirmation | [11 empty] | 67462 | 67523
67561 | Feature | 3. Service Entitlements | Input: Active Contract Activities: 3.1 Create Entitlements, 3.2 Link Contract and Assets, 3.3 Define Entitled Services, 3.4 Track Usage and Validity Output: Validated Service Coverage | [11 empty] | 67557 | 67561
67562 | Feature | 4. Install Base Management | Input: Customer, Location and Asset data Activities: 4.1 Create Installed Products, 4.2 Link Account and Locations, 4.3 Maintain warranty and serial data, 4.4 Govern Installed-base quality Output: Trusted Installed Base record | [11 empty] | 67557 | 67562
67574 | Feature | 1. Case Intake & Classification | Input: Customer, Partner or system generated case Activities: 1.1 Customer raises request, 1.2 Partner/distributor raises request, 1.3 Installed Base/entitlement issue, 1.4 Tier 1/Tier 2 escalations Output: Classified Service Case | [11 empty] | 67572 | 67574
| User Story | Replicate Pipedrive lead capture and lead stages in Dynamics 365 CRM | As a North America sales operations lead, I need to capture trade-show and field leads in Dynamics 365 CRM using the same lead stages the team follows in Pipedrive today, so that the team keeps one place to follow up and report on leads once Pipedrive is retired. | [9 empty] | - Trade-show and field leads can be recorded in CRM and appear in a single lead list for follow-up - The lead stages used in Pipedrive today are configured in CRM (exact stage list pending the Pipedrive stage review task) - Leads exported from Pipedrive can be imported into CRM (import into CRM versus Zinfi to be confirmed) |  | 67461 | 67488
| User Story | Configure a global opportunity pipeline with standard stages | As a sales operations lead, I need to configure one globally standardized set of opportunity stages for the phase 1 implementation, so that opportunity progress is tracked consistently while future stage changes need no custom development. | [9 empty] | - Opportunity pipeline stages are configured globally for phase 1 (no per-region stage variation at launch) - Stage names and number of stages can be changed through configuration without custom development - Each stage can require mandatory information to be captured before the user can progress to the next stage - Forecast qualifiers such as best case and commit can be recorded on an opportunity (final stages, gates and qualifier definitions pending DQ-009) |  | 67461 | 67489
| User Story | Capture a 12-month rolling partner forecast in Zinfi and synchronize it to CRM | As a channel sales manager for the home and public (AED) business, I need to have partners maintain a 12-month rolling forecast on the main consumable and equipment articles in Zinfi that synchronizes to CRM, so that partner demand is visible in CRM without requiring deal-by-deal opportunity entry for the AED business. | [9 empty] | - Partner can enter and update a 12-month rolling forecast by main consumable and equipment article in Zinfi - Forecast entries and updates made in Zinfi are synchronized to CRM and visible to Heartstream users - For the home and public (AED) business the forecast is held at article level and not as individual opportunities |  | 67461 | 67489
| User Story | Allow low-value direct quotes without creating a full opportunity | As a direct sales representative, I need to create a quote for a single low-value item against a shell opportunity instead of creating a full opportunity each time, so that small requests such as one battery or one roll of paper are not delayed by opportunity set-up. | [9 empty] | - A quote for a single low-value item can be created without creating a new full opportunity for each request - Every quote is still linked to an opportunity; for low-value items this is a shell/placeholder opportunity, so no orphan quotes exist - Quotes for standard items continue to require a linked opportunity - Definition of low-value and shell-opportunity mechanics pending DQ-008 |  | 67461 | 67492
| User Story | Run partner due diligence and approval in Zinfi before onboarding is finalized | As a partner onboarding reviewer, I need to complete partner intake, due diligence, contract signature and approval in Zinfi, with onboarding communications sent from Zinfi, so that only qualified partners are enrolled through one consistent journey for distributors, dealers, manufacturer's representatives and service partners. | [9 empty] | - Onboarding is initiated by Heartstream sales and handed to sales operations/back office; partners do not self-register - Due diligence is performed with commercial and contracts departments and the approval is recorded in Zinfi - Onboarding communications to the partner are sent from Zinfi - The same onboarding journey applies to distributors, dealers, manufacturer's representatives and service-only partners, with partner type captured on the record |  | 67462 | 67506
| User Story | Capture reseller sales-partner contract terms | As a contracts team member, I need to record a sales-partner contract with the product categories the partner may sell, and the discount and rebate terms, so that quotations and orders for that partner are priced correctly. | [9 empty] | - Contract stores the products and product categories the partner is authorized to distribute (for example AED only, professional only) - Contract stores discounts as a percentage off list price, which can differ by product group, by hardware versus supplies, and for specific materials - Contract stores rebate terms - Geographic territory limits are stated in contract wording and addendum and are not hard-wired restrictions in the system |  | 67462 | 67507
| User Story | Capture service-partner contract terms for spare-part discounts and service levels | As a contracts team member, I need to record a service-partner contract with discounts on individual service part numbers and applicable service levels, so that service partners are priced correctly and held to agreed service terms. | [9 empty] | - Contract stores contracted discounts on individual service part numbers - Contract stores applicable SLA timelines (SLA content per UST understanding, to be confirmed with contract samples) - Sales-partner and service-partner contracts are recorded as distinct contract types |  | 67462 | 67507
| User Story | Set partner contract duration within agreed minimum and maximum | As a contracts team member, I need to set contract durations within the agreed minimum and maximum for each contract type, so that contracts are created within the business limits seen today. | [9 empty] | - Reseller (distributor) contract duration can be set from a minimum of 1 year up to 3 years - Direct customer contract duration can be set up to 5 years - Contract start and end dates reflect the selected duration (limits as observed in workshop, to be confirmed as enforced rules) |  | 67462 | 67507
| User Story | Alert the contracts team to partner contracts nearing expiry | As a contracts team member, I need to be alerted when a partner contract is nearing expiry, so that contracts are renewed or extended before they lapse. | [9 empty] | - Contracts nearing expiry are identified by the system and the contracts team is notified - A renewed or extended contract keeps the partner's history and shows the new term dates (alert lead time to be defined) |  | 67462 | 67507
| User Story | Manage partner contracts in Zinfi and synchronize contract data to CRM | As a contracts team member, I need to manage partner contracts in Zinfi and synchronize the contract data to Dynamics 365 CRM for visibility, so that partners can see their final approved contract and Heartstream users see the same terms, while only the contracts department can change content. | [9 empty] | - Contract discussions and the final approved contract are available to the partner in Zinfi - Contract data is synchronized from Zinfi to CRM for visibility - Only the contracts department can change contract content once signed; other users cannot (system of record pending DQ-011) |  | 67462 | 67507
| User Story | Support mid-contract list price updates with notice period | As a contracts team member, I need to update list prices during an active contract term and notify partners with the notice period in the contract, so that new pricing applies only after partners are informed. | [9 empty] | - List price on an active contract can be updated during the contract term - Updated pricing is not effective until the notice period (typically 60 days) has elapsed from notification - The partner receives the updated price file at the start of the notice period |  | 67462 | 67508
| User Story | Sync approved partner record from Zinfi to CRM only after onboarding is finalized | As a CRM solution owner, I need to sync a partner account and contact record from Zinfi to Dynamics 365 CRM only after the partner's onboarding is finalized (due diligence, required training and contract signature complete), so that CRM only reflects authorized, business-ready partners. | [9 empty] | - Partner record is not created in CRM until the Zinfi onboarding status is Approved (definition of onboarded pending DQ-001) - An approved partner triggers creation of an account record and an associated contact record in CRM - The partner account number in Zinfi is linked to the corresponding CRM account number - The synced account is the same partner record later used for invoicing |  | 67462 | 67510
| User Story | Scope partner record visibility to originating legal entity | As a Dynamics CRM user, I need to see a synced partner record only within the legal entity of the partner's originating region, so that partner data is not exposed across unrelated legal entities. | [9 empty] | - A partner record created for a given region is synced to and visible only in the corresponding CRM legal entity - Users logged into a different legal entity cannot see the partner record - One partner maps to exactly one legal entity for the current scope (no multi-region partners) |  | 67462 | 67510
| User Story | Assign single record owner with legal-entity-wide read visibility | As a sales operations lead, I need to assign one owner (the approving channel or account manager, or a team) to the synced partner record while keeping it viewable by all CRM users in that legal entity, so that accountability is clear without restricting day-to-day visibility. | [9 empty] | - Partner record has exactly one owner (user or team) assigned on sync - Any authenticated CRM user within the partner's legal entity can view the record - Users other than the owner cannot edit the record |  | 67462 | 67510
| User Story | Enforce read-only partner record with approval-based edit exception | As a CRM administrator, I need to enforce the synced partner record as read-only for all users by default, so that master partner data is not changed without oversight; a future approval flow may grant the record owner edit rights. | [9 empty] | - Partner record fields are non-editable for all CRM users, including the owner, immediately after sync - Adding a new partner location or warehouse creates a new record and is not an edit to the existing partner record - Any future edit capability for the owner is gated behind an approval flow and not open direct edit (approval design pending DQ-007) |  | 67462 | 67510
| User Story | Capture required account-planning data points in CRM | As a sales operations lead, I need to capture in Dynamics 365 CRM only the account-planning data points required for CRM visibility, with the full planning performed in Zinfi, so that CRM holds the required data without duplicating the planning workflow. | [9 empty] | - Partner account planning (creation and approval) is performed in Zinfi and not in CRM - CRM stores only the planning data points confirmed as required (data points pending DQ-010) |  | 67462 | 67510
| User Story | Sync partner training completion status to CRM | As a partner onboarding reviewer, I need to synchronize the partner's required training completion status from Zinfi to Dynamics 365 CRM, so that training can be confirmed as part of onboarding approval without duplicating the learning management system in CRM. | [9 empty] | - Training status values recorded in Zinfi are synchronized to a training status field on the CRM partner record - CRM stores training status only and not training content or course detail |  | 67462 | 67512
| User Story | Report lead closure outcomes by partner for distributed leads | As a channel manager, I need to report on how many leads distributed to each partner were closed and with what outcome, so that partners who close no leads are identified quickly. | [9 empty] | - Partner status updates on distributed leads made in Zinfi are visible in CRM - A CRM report or view shows leads distributed, leads closed and the outcome per partner - Partners with no closed leads can be identified from the report |  | 67462 | 67514
| User Story | Create and distribute leads from CRM to partners via Zinfi | As a Heartstream sales or marketing team member, I need to create a lead in Dynamics 365 CRM and have it synchronized to Zinfi for the assigned partner, so that partners can act on leads generated by Heartstream without direct CRM access. | [9 empty] | - A lead created in CRM by sales or marketing and assigned to a partner is synchronized to Zinfi and visible to that partner - Lead status updates made by the partner in Zinfi are synchronized back to CRM - Partners do not work leads inside CRM |  | 67462 | 67515
| User Story | Allow account managers to create and maintain their own leads | As an account manager, I need to create and maintain leads I identify in the field and assign them to partners, so that I am not dependent on the marketing team to record leads I generate through prospecting. | [9 empty] | - An account manager can create a new lead record directly in CRM - An account manager can assign a self-created lead to a partner - Self-created leads follow the same synchronization process to Zinfi as marketing-sourced leads |  | 67462 | 67515
| User Story | Allow partners to optionally register their own leads in Zinfi | As a partner, I need to register a lead I generated myself directly in Zinfi, so that leads I find independently are tracked and visible to Heartstream in addition to leads assigned to me. | [9 empty] | - A partner can create a lead in Zinfi that was not assigned by Heartstream - The partner-created lead is synchronized to CRM for visibility - Partner lead registration is optional and not a blocking condition for partners (adoption uncertain, see DQ-002) |  | 67462 | 67515
| User Story | Synchronize leads and opportunities two ways between Zinfi and CRM | As a CRM solution owner, I need to keep leads and opportunities in step between Zinfi and Dynamics 365 CRM through two-way synchronization, with partners working only in Zinfi, so that users do not need to log into two systems and partners do not need CRM licenses. | [9 empty] | - A change to a lead or opportunity made in CRM is synchronized to Zinfi - A change made in Zinfi is synchronized to CRM - Partners and contracted sales representatives have no direct access to Dynamics 365 CRM and work through Zinfi |  | 67462 | 67516
| User Story | Share opportunity notes and customer communication between partner and Heartstream users | As a partner or Heartstream team member collaborating on an opportunity, I need to see notes and customer communications added by either side on the same opportunity, so that we avoid duplicate or conflicting outreach to the same customer. | [9 empty] | - Notes added to an opportunity by a partner in Zinfi are visible to Heartstream users in CRM, and the reverse - Customer communications for partner-managed opportunities are sent from Zinfi and are visible to Heartstream users in CRM - Customer communications sent by internal sales users from CRM are visible to the partner in Zinfi |  | 67462 | 67516
| User Story | Register partner-led opportunities in Zinfi and synchronize them to CRM | As a channel sales manager for the professional business, I need to have partners register opportunities against end customers in Zinfi that synchronize to CRM, so that Heartstream can see the professional-business funnel by hospital and customer. | [9 empty] | - A partner can register an opportunity for an end customer in Zinfi - The registered opportunity is synchronized to CRM and linked to the end-customer account - Deal-by-deal registration is expected for the professional business; for the home and public (AED) business partner demand is tracked through forecast instead (see DQ-013) |  | 67462 | 67516
| User Story | Import batches of partner opportunities into Zinfi from partner CRM systems | As a partner in the professional business, I need to upload a batch of opportunities I already hold in my own CRM instead of re-entering them one by one, so that I avoid duplicate work and keep supplying Heartstream with opportunity visibility. | [9 empty] | - A partner can upload multiple opportunities in one batch in Zinfi - Uploaded opportunities are synchronized to CRM and linked to the end-customer account - Upload method and format are pending confirmation (see DQ-013) |  | 67462 | 67516
| User Story | Flag an opportunity as a registered deal by product or solution category | As a sales operations lead, I need to have the opportunity flagged as a registered deal based on the product or solution category selected, so that professional-line deals follow single-partner rules while AED-line opportunities can have several partners. | [9 empty] | - Opportunity records a product or solution category selected from a list - Selecting a category configured as registered-deal category applies the single-partner deal registration rule - Selecting a category not configured for deal registration allows multiple partners on the same opportunity |  | 67462 | 67516
| User Story | Prevent duplicate deal registration for the same customer opportunity | As a channel manager, I need to block a second partner from registering a deal against an end customer that already has a registered deal in the professional business, so that channel conflicts over the same deal are avoided. | [9 empty] | - Attempting to register a deal for a customer that already has a registered deal shows a blocking notification - For large professional deals the block applies at opportunity creation and not only when the opportunity is converted to a deal (large-deal definition pending DQ-012) - The existing registered deal stays assigned to the original registering partner |  | 67462 | 67516
| User Story | Mark individual deals as registered case by case for any product line | As a Heartstream channel manager, I need to mark an individual opportunity as a registered deal regardless of product line, so that enterprise-type deals in the home and public business can be protected for one partner and reported separately. | [9 empty] | - A Heartstream user can set a deal-registration indicator (checkbox or list value) on any opportunity - Only Heartstream users can confirm that a deal is registered; partners cannot set the indicator - Registered deals can be filtered and reported separately from standard opportunities (mechanism pending DQ-012) |  | 67462 | 67516
| User Story | Show open opportunities and registered deals on the customer account | As a channel manager, I need to see all open opportunities and registered deals for an end customer from the customer account, so that channel conflicts are identified before a second partner is supported. | [9 empty] | - Customer account lists open opportunities and registered deals linked to it - The list identifies the partner associated with each opportunity or registered deal - Opportunities and deals registered in Zinfi appear on the customer account after synchronization |  | 67462 | 67516
| User Story | Derive quote pricing from the partner's active contract | As a partner or sales user, I need to have quote pricing derived automatically from the partner's active contract terms, so that quotations are consistent with agreed contractual pricing without manual lookup. | [9 empty] | - Quote line pricing defaults to the price derived from the partner's active contract - The quote is linked to an opportunity and, through it, to the contracted partner - Discounts defined in the contract by product group or material are reflected in the quote line price |  | 67462 | 67517
| User Story | Route additional discount beyond contract through tiered approval | As a partner or sales user, I need to route a discount request above the contracted price through a tiered approval chain (partner account manager, then regional sales director, then head of finance), so that discounts beyond contract are authorized before the quote proceeds. | [9 empty] | - Discount within contracted terms requires no additional approval - Discount above contract up to the first threshold requires partner account manager approval - Discount above the next threshold requires regional sales director approval and above the highest threshold requires head of finance approval (threshold values pending DQ-014) - The approver receives a prompt notification of the pending approval and the quote cannot proceed until approved |  | 67462 | 67517
| User Story | Honor quoted pricing for open quotes through the validity period | As a sales user, I need to keep the price on an open quote valid for the quote validity period even if list prices change, so that customers receive the price they were quoted. | [9 empty] | - Quote validity defaults to 60 days - An open quote keeps its quoted price until expiry even when contract list prices are updated - If the old price needs extra discount to be honored, that discount follows the approval flow |  | 67462 | 67517
| User Story | Re-trigger approval on pricing or configuration revision, not on date-only changes | As an approver, I need to have approval re-triggered when a revision to a quote changes pricing or configuration, and not when only the requested delivery date changes, so that approval effort is focused on changes that affect commercial terms. | [9 empty] | - Editing price or product configuration on an unconfirmed quote re-triggers the approval workflow - Editing only the requested delivery date does not re-trigger approval - The existing quote is revised and no new quote is required - Revisions are only permitted before the sales order is confirmed |  | 67462 | 67517
| User Story | Request time-bound part-number discounts outside an opportunity | As a sales manager, I need to request a discount on a part number for a defined period that is not tied to a single opportunity, so that a blanket discount can be applied to several customers without creating opportunities. | [9 empty] | - A discount request can be raised for a part number with a start and end date without an opportunity - The request follows an approval workflow with notifications to approvers (approver chain pending DQ-014) - After the end date the discount no longer applies to new quotes |  | 67462 | 67519
| User Story | Convert an approved quote into an order with last-minute configuration changes | As a partner or sales user, I need to convert an approved quote into an order, adding the requested delivery date and making final configuration adjustments, so that the order starts from the quoted contractual pricing and needs little rework. | [9 empty] | - Only an approved quote can be converted into an order - The order carries pricing from the approved quote - A configuration or pricing change during conversion follows the revision and approval rules |  | 67462 | 67521
| User Story | Validate partner purchase-order pricing against contract pricing at order entry | As an order management team member, I need to have orders received through a purchase order checked against the partner's contract pricing, so that mispriced orders are caught at entry instead of being sent back later. | [9 empty] | - Order lines created from a partner purchase order are compared with the partner's contract prices - A difference between purchase order price and contract price is flagged before the order can be confirmed - Orders that match contract pricing proceed without manual price correction (quote versus PO model pending DQ-015) |  | 67462 | 67521
| User Story | Place partner orders through the Zinfi portal | As a partner, I need to place an order through the Zinfi portal, so that I can order without Dynamics 365 access. | [9 empty] | - A partner can create an order in Zinfi - The order is synchronized to CRM and visible to Heartstream users - The same channel is expected for contracted direct-sales representatives (order entry for North America pending DQ-006) |  | 67462 | 67521
| User Story | Require requested delivery date on every order | As a partner, I need to provide a requested delivery date (RDD) on the order, so that Heartstream schedules delivery to the customer's actual need date. | [9 empty] | - RDD is a mandatory field on the sales order before fulfillment starts - RDD is captured on the order and not on the quote - An order cannot be confirmed without an RDD |  | 67462 | 67521
| User Story | Support line-level requested delivery dates for staggered shipments | As a partner, I need to request different delivery dates for different line items on one order, so that annual orders can ship in stages without being split into separate orders. | [9 empty] | - Each order line can carry its own RDD - A single order can contain lines with different delivery dates - The default is one RDD per order; staggered line dates are a controlled exception (control rules pending DQ-018) |  | 67462 | 67521
| User Story | Confirm the sales order and transmit it to F&O for fulfillment | As an order management team member, I need to confirm a validated sales order and send it to Dynamics 365 Finance & Operations, so that fulfillment and invoicing can start. | [9 empty] | - A confirmed sales order in CRM is transmitted to F&O for fulfillment - Unconfirmed or unapproved orders are not transmitted - After transmission the order continues into the fulfillment process and invoicing is handled in the ERP |  | 67462 | 67522
| User Story | Lock order from cancellation and edit after a defined fulfillment status | As an order management team member, I need to block cancellation and edit requests on a sales order once it reaches a defined fulfillment status, so that orders already built or shipped are not disrupted within the application. | [9 empty] | - Order status updates received from F&O are shown in CRM and Zinfi - Once the order reaches the configured lock status, cancellation and edit actions are blocked - A blocked cancellation or edit attempt is rejected with a clear message (lock status pending DQ-017) |  | 67462 | 67523
| User Story | Show order, shipment and invoice status to partners in Zinfi | As a partner, I need to see the current order, shipment and invoice status in Zinfi, so that I can inform my customer about delivery without contacting Heartstream. | [9 empty] | - Key statuses updated in F&O are synchronized to CRM and then to Zinfi - Partner can view current fulfillment and shipment status for its own orders in Zinfi - Status shown in Zinfi matches the status in CRM |  | 67462 | 67523
| User Story | Provide required customs and shipment documents for applicable regions | As a partner responsible for customs clearing, I need to receive the shipment documents required for my country with each shipment, so that customs clearing proceeds without delay. | [9 empty] | - The system identifies the required document set for the destination country of the shipment - Required documents (for example signed invoice, certificate of origin, packing list, product sheets) are available to the partner with the shipment confirmation - Document requirements can be configured per country (document list pending DQ-019) |  | 67462 | 67523
| User Story | Record post-warranty parts coverage against serial numbers for service partners | As a service operations lead, I need to record multi-year parts coverage that a service partner buys for specific device serial numbers, so that covered serial numbers can be validated when the customer or partner contacts Heartstream. | [9 empty] | - Coverage can be recorded for a list of serial numbers with a start and end date, typically one to five years - Coverage includes the first-year warranty and the purchased post-warranty term - Coverage and its end date can be retrieved by serial number - Existing coverage migrated from current systems is held in the same structure (notification of service distributors pending DQ-023) |  | 67557 | 67561
| User Story | Create install base record on delivery for serialized hardware | As a compliance and service stakeholder, I need to create an install base record for serialized hardware at the agreed trigger milestone, preferably delivery rather than shipment, so that the install base reflects the customer's actual receipt of the product. | [9 empty] | - Install base record is created for the serial number at the agreed trigger (delivery preferred; exact trigger by product type pending DQ-004) - Install base record permanently retains the original order and ship-to location - The record is available in CRM so service and compliance users can verify the customer name and address before servicing a device |  | 67557 | 67562
| User Story | Update current install base location through a quick controlled process | As a service and compliance stakeholder, I need to update the current name and address of a serial number quickly through a lightweight controlled process, so that regulatory compliance and recall notifications reach the right customer without a large install base team. | [9 empty] | - The current name and address of a serial number can be updated - The original order location is retained after the current location is updated - Updates follow a lightweight approval step (approver and owner pending DQ-005) |  | 67557 | 67562
| User Story | Allow partner-initiated install base change request via Zinfi | As a partner, I need to submit a request in Zinfi to update the location or end-customer information for a serial number, so that Heartstream install base stays accurate without giving me direct edit access. | [9 empty] | - A partner can submit a location or customer change request for a serial number from Zinfi - The partner cannot directly edit the install base record - The request reaches CRM for review and is applied by the owning team (owner pending DQ-005) |  | 67557 | 67562
| User Story | Synchronize partner-raised case escalation from Zinfi to CRM for triage | As a partner, I need to raise an escalation request from Zinfi when I cannot resolve a customer case myself, so that the case is triaged by the right Heartstream team. | [9 empty] | - A partner can raise a case escalation in Zinfi - The escalation synchronizes to CRM and is available for triage - Partners handle initial resolution with the customer and escalate only when needed (detailed triage and ownership in the dedicated case-management session) |  | 67572 | 67574
| Task | Circulate detailed minutes of meeting and record open/parking-lot items in ADO | Owner: UST facilitator. Share MoM, assumptions and open points; assign requested information and formats to named owners. Source 3:11:50-3:12:17. | [7 empty] | Day 2\CRM
| Task | Invite Zinfi team members to upcoming workshops in the series | Owner: Heartstream workshop coordinator. Zinfi was not on this call. Source 0:14-0:29, 6:52-7:44. | [7 empty] | Day 2\CRM
| Task | Share Zinfi contact name with Heartstream workshop coordinator | Owner: Heartstream Europe representative (Vince). Zinfi team member who worked with the earlier program lead. Source 7:56-8:09. | [7 empty] | Day 2\CRM
| Task | Define mandatory partner and contact fields with Zinfi for CRM account creation | Owner: UST with Zinfi team. Fields captured in Zinfi, fields flowing to Dynamics, and fields shown on the CRM partner record. Source 25:31-27:14. | [7 empty] | Day 2\CRM
| Task | Validate Zinfi platform capabilities raised in the workshop with the Zinfi team | Owner: UST with Zinfi team. Lead distribution to partners, batch opportunity upload, locking order cancellation, order entry for contracted representatives, direct-customer contract and fixed multi-year pricing support. Source 50:23-50:46, 2:07:34-2:08:37, 2:51:13-2:51:22. | [7 empty] | Day 2\CRM
| Task | Review the sample complex partner contract requested from Heartstream | Owner: Heartstream contracts contact (Patrice) to provide, UST to review. Source 2:05:20-2:05:32, 2:14:10. | [7 empty] | Day 2\CRM
| Task | Schedule a dedicated session on direct customer contracts | Owner: UST facilitator. Hospital, EMS and group purchasing organization contracts; Heartstream lead asked to be told which call covers it. Source 2:05:42-2:06:16. | [7 empty] | Day 2\CRM
| Task | Confirm and communicate the order-entry workflow for North America contracted direct-sales representatives | Owner: UST facilitator. To be conveyed before the workflow is finalized. Source 2:22:29-2:23:51. | [7 empty] | Day 2\CRM
| Task | Provide region-specific opportunity stage and review-gate details | Owner: Heartstream regional sales leads. Europe presentation was shared in chat; other regions' stages still needed. Source 1:27:07-1:27:30, 1:32:39-1:32:54. | [7 empty] | Day 2\CRM
| Task | Document current Pipedrive lead stages and trade-show lead flow for North America | Owner: UST with Heartstream North America sales operations. Source 1:22:12-1:24:08. | [7 empty] | Day 2\CRM
| Task | Connect UST with the Europe regional service manager for service-partner details | Owner: Heartstream Europe representative (Vince). Source 2:33:33-2:33:56. | [7 empty] | Day 2\CRM
| Task | Plan migration of existing service entitlements by serial number into Dynamics 365 | Owner: UST data migration lead with Heartstream service. About 40,000 devices globally with one to four years of coverage remaining must be available on day one. Source 2:31:58-2:33:12. | [7 empty] | Day 2\CRM
| Task | Provide discount approval matrix with approvers and thresholds per region | Owner: Heartstream regional sales and finance leads. Source 2:15:52-2:17:06. | [7 empty] | Day 2\CRM
| Task | Schedule follow-up sessions on partner case management, service and quality alignment, marketing lead distribution, and opportunity lifecycle | Owner: UST facilitator. Source 51:04-51:08, 1:31:53-1:32:07, 3:07:48-3:08:19, 3:10:32-3:11:13. | [7 empty] | Day 2\CRM
| Issue | Definition of onboarded status and CRM sync point not confirmed | DQ-001 - Risk: Statements differed on whether the partner syncs to CRM at Zinfi approval or only after contract signature and training completion (22:54-25:31). Impact: Sync trigger, partner status values and CRM account creation cannot be finalized. Mitigation: Confirm the status that marks a partner as onboarded in the fit-gap session. | [7 empty] | Day 2\CRM
| Issue | Partner adoption of self-registered leads uncertain | DQ-002 - Risk: Partners keep leads in their own CRMs and are reluctant to re-enter them; contractual obligation or incentives were suggested (1:00:05-1:00:57, 1:18:41-1:18:53). Impact: Partner-sourced lead volume in Zinfi and CRM may be low. Mitigation: Treat partner lead registration as optional and revisit incentives later. | [7 empty] | Day 2\CRM
| Issue | Direct customer contract model undefined | DQ-003 - Risk: Direct customer contracts (hospital, EMS, group purchasing organizations) including multi-year fixed pricing with price look-back were raised but not detailed (2:05:42-2:08:37). Impact: Direct-sales contract solutioning cannot start; North America direct volume is significant. Mitigation: Dedicated session requested by Heartstream. | [7 empty] | Day 2\CRM
| Issue | Install base creation trigger by product type undecided | DQ-004 - Risk: Shipment is today's trigger, delivery preferred; software may trigger at activation (2:55:33-3:05:34). Impact: Install base timing and data accuracy for compliance remain undefined. Mitigation: Confirm trigger per product type in install base modelling sessions. | [7 empty] | Day 2\CRM
| Issue | Ownership of install base location changes in CRM undefined | DQ-005 - Risk: Who owns and applies location changes, including partner requests, was not answered (3:00:30-3:01:11, 3:06:11-3:06:26). Impact: Approval flow and task routing cannot be designed. Mitigation: Parking lot item for install base design. | [7 empty] | Day 2\CRM
| Issue | North America contracted direct-sales rep system access undecided | DQ-006 - Risk: Contracted direct-sales reps in North America do not have Dynamics CRM access (named-user licensing); how they place direct orders (Zinfi or another channel) is not decided (2:10:34-2:12:20, 2:22:29-2:23:51). Impact: Direct order entry process for North America cannot be solutioned. Mitigation: Facilitator to confirm workflow in follow-up. | [7 empty] | Day 2\CRM
| Issue | Edit rights and approval flow for synced partner records undecided | DQ-007 - Risk: Whether the owner or a super user may change partner name, address or phone through an approval flow was left open; record is read-only for now (29:12-40:06). Impact: Partner data changes after onboarding have no defined route. Mitigation: Revisit with finance master data and contracts teams. | [7 empty] | Day 2\CRM
| Issue | Shell-opportunity quoting for low-value items undefined | DQ-008 - Risk: Heartstream quotes single low-value items and today uses dummy opportunities; e-store is not available for hospital purchases (2:38:44-2:41:04). Impact: Quote creation mechanics and reporting impact are open. Mitigation: Solutioning session. | [7 empty] | Day 2\CRM
| Issue | Opportunity stages, review gates and forecast qualifiers not agreed | DQ-009 - Risk: Regions use different stage sets (four to six stages, P1-P4, best case, commit) and some have no stage definition (1:24:20-1:32:54). Impact: Pipeline configuration and mandatory-information gates cannot be finalized. Mitigation: Region details to be provided and consensus taken in detailed discussions. | [7 empty] | Day 2\CRM
| Issue | Account-planning data points and partner-type variations undefined | DQ-010 - Risk: Who creates and approves partner plans and any regional variation is unknown; North America has five agreement types (stocking distributor, non-stocking distributor, manufacturer's rep, just-in-time distributor, federal and military partner) (40:10-44:11). Impact: CRM data model for partner type and planning is open. Mitigation: Take up with Zinfi team. | [7 empty] | Day 2\CRM
| Issue | Contract ownership and system of record undefined | DQ-011 - Risk: Whether contracts live in Zinfi or D365 is open, including Europe partners working in their own CRM and LATAM contracts handled by the Europe team with a Day 2 decision pending (45:30-46:39, 1:47:33-1:50:02). Impact: Contract visibility, ownership and integration design cannot start. Mitigation: Contract samples and follow-up session. | [7 empty] | Day 2\CRM
| Issue | Large-deal definition and case-by-case deal registration mechanism undefined | DQ-012 - Risk: The registration indicator (checkbox or list), the definition of a large deal and handling for the home and public business are open (1:12:56-1:16:22). Impact: Channel conflict rules cannot be finalized. Mitigation: Parking lot item for opportunity design. | [7 empty] | Day 2\CRM
| Issue | Approach to avoid double entry of partner opportunities and forecasts undefined | DQ-013 - Risk: Partners hold opportunities in their own CRM (Salesforce in Europe) and forecasts in Excel (44:19-49:15, 1:02:05-1:02:40). Impact: Partners may refuse re-entry; funnel visibility is at risk. Mitigation: Evaluate batch import and integration options with the Zinfi team. | [7 empty] | Day 2\CRM
| Issue | Discount approval thresholds and approvers per region not defined | DQ-014 - Risk: Three to four approval tiers were described for Europe and North America but thresholds and approvers are not documented (2:15:52-2:17:06, 2:34:34-2:38:00). Impact: Approval workflow cannot be configured; speed target of about one day needs notifications. Mitigation: Approval matrix requested. | [7 empty] | Day 2\CRM
| Issue | Partner quoting versus purchase-order ordering model differs by region | DQ-015 - Risk: Rest of world uses a quote tool with approval, North America partners send POs against contract pricing (2:00:00-2:02:57, 2:14:25-2:15:12). Impact: Whether one process or two is built is open. Mitigation: Review contract types and decide in solutioning. | [7 empty] | Day 2\CRM
| Issue | Quoting experience consistency across CRM, Zinfi and e-store undecided | DQ-016 - Risk: Europe wants the same look and feel across channels and raised an external configuration tool; UST will first evaluate out-of-the-box Dynamics quoting (2:12:21-2:13:20). Impact: Quote tool choice may add cost and integration. Mitigation: Fit-gap on standard quoting. | [7 empty] | Day 2\CRM
| Issue | Order lock status and Zinfi cancellation lock capability undefined | DQ-017 - Risk: The status at which orders freeze and Zinfi's ability to lock partner requests are unknown; cancellations by phone cannot be controlled by the application (2:50:06-2:52:52). Impact: Order protection rules are open. Mitigation: Define lock status with manufacturing. | [7 empty] | Day 2\CRM
| Issue | Controlled approach for staggered delivery on annual partner orders undefined | DQ-018 - Risk: Europe saw full-year stock delivered at once during migration and now pushes one RDD per order; North America needs staggered delivery (2:44:59-2:47:19). Impact: Order structure and approval controls are open. Mitigation: Decide controlled way of working. | [7 empty] | Day 2\CRM
| Issue | Customs and shipment document sets per country not defined | DQ-019 - Risk: Required documents differ by country and product (for example batteries need product sheets) (2:53:02-2:55:27). Impact: Document capture and delivery cannot be designed. Mitigation: Heartstream to provide the document list per country. | [7 empty] | Day 2\CRM
| Issue | Device location capture for distributor-shipped devices undecided | DQ-020 - Risk: Drop-ship to end customers gives accurate install base; shipping to distributors depends on distributor lists within three working days for regulatory notices (3:00:05-3:04:16). Impact: Install base accuracy and compliance for distributor-shipped devices. Mitigation: Decide global versus regional practice for Day 2. | [7 empty] | Day 2\CRM
| Issue | Partner role in capturing customer feedback and patient events undecided | DQ-021 - Risk: Distributors currently report to a defined quality location; whether Zinfi plays a role is open (3:10:32-3:11:13). Impact: Quality and regulatory reporting route. Mitigation: Align in the service workshop with Quality. | [7 empty] | Day 2\CRM
| Issue | Zinfi platform capabilities not validated because Zinfi team was absent | DQ-022 - Risk: Zinfi team members were not on the call and North America participants are unfamiliar with Zinfi (0:14-0:29, 14:52-15:19, 41:00-41:03). Impact: Assumptions about Zinfi behavior in these stories are unvalidated. Mitigation: Include Zinfi in the series going forward. | [7 empty] | Day 2\CRM
| Issue | Notification of service distributors when end customers buy coverage directly undecided | DQ-023 - Risk: Question whether a service distributor is told when a customer buys coverage directly was not answered (2:31:38-2:33:12). Impact: Service coverage and distributor communication rules. Mitigation: Take up with the service managers. | [7 empty] | Day 2\CRM

## MappingReview
Story Title | EPIC ID | Epic Title | FEATURE ID | Feature Title | Confidence | Rationale | Source (speaker/timestamp) | Status (Mapped/UNMAPPED)
Replicate Pipedrive lead capture and lead stages in Dynamics 365 CRM | 67461 | 01. B2B Direct Sales | 67488 | 3. Lead Assessment | Medium | Epic 01 Feature 3 'Lead Assessment' (3.1 Generate Leads, 3.2 Score & Qualify Leads) fits lead capture and staging; Epic 02 lead features are partner-specific. Pipedrive retirement was stated by UST and not contested. | 1:22:12-1:24:08 | Mapped
Configure a global opportunity pipeline with standard stages | 67461 | 01. B2B Direct Sales | 67489 | 4. Opportunity Management | Medium | Feature 4 Opportunity Management activity 4.2 'Manage Sales Pipeline' matches stage configuration. Partner variant Epic 02 Feature 11 (2.2 Track Opportunity Progression) was the alternative; Epic 01 chosen because stages are common to all B2B opportunities and facilitator scoped the discussion to B2B opportunities. | 1:24:20-1:32:54 | Mapped
Capture a 12-month rolling partner forecast in Zinfi and synchronize it to CRM | 67461 | 01. B2B Direct Sales | 67489 | 4. Opportunity Management | Medium | Only forecast activity in the Epics is 4.5 'Manage Sales Forecast' in Epic 01 Feature 4. Epic 02 Feature 11 has no forecast activity. Flagged for SME confirmation whether a reseller-side forecast Feature is needed. | 44:19-45:20, 1:04:30-1:05:01 | Mapped
Allow low-value direct quotes without creating a full opportunity | 67461 | 01. B2B Direct Sales | 67492 | 7. Quotation & Pricing | Medium | Scenario described is direct quoting to hospitals; Epic 01 Feature 7 'Quotation & Pricing' (7.1 Create Quotations) is the direct-sales quoting Feature. Epic 02 Feature 12 is the partner equivalent. | 2:38:10-2:41:04 | Mapped
Run partner due diligence and approval in Zinfi before onboarding is finalized | 67462 | 02. B2B Direct Through Reseller | 67506 | 2. Partner Onboarding & Qualification | High | Feature 2 'Partner Onboarding & Qualification' (2.1 Capture Applications, 2.2 Evaluate Eligibility, 2.3 Approve Enrollment) matches the due diligence and approval discussion. | 16:28-25:31, 20:04-20:44 | Mapped
Capture reseller sales-partner contract terms | 67462 | 02. B2B Direct Through Reseller | 67507 | 3. Partner Contracting & Commercial Setup | High | Feature 3 activities 3.2 'Define Partner Pricing & Discounts' and 3.4 'Establish Partner Agreements'. | 1:52:20-1:53:17, 1:55:14-1:58:45, 2:19:18-2:19:58 | Mapped
Capture service-partner contract terms for spare-part discounts and service levels | 67462 | 02. B2B Direct Through Reseller | 67507 | 3. Partner Contracting & Commercial Setup | Medium | Feature 3 'Partner Contracting & Commercial Setup' covers partner agreements for sales and service partners. | 1:52:28-1:53:39, 2:24:25-2:28:06 | Mapped
Set partner contract duration within agreed minimum and maximum | 67462 | 02. B2B Direct Through Reseller | 67507 | 3. Partner Contracting & Commercial Setup | Medium | Feature 3 activity 3.4 'Establish Partner Agreements'. | 2:18:02-2:20:47 | Mapped
Alert the contracts team to partner contracts nearing expiry | 67462 | 02. B2B Direct Through Reseller | 67507 | 3. Partner Contracting & Commercial Setup | Medium | Feature 3 covers agreements; no dedicated renewal Feature exists for partner contracts in Epic 02. | 2:17:18-2:18:33 | Mapped
Manage partner contracts in Zinfi and synchronize contract data to CRM | 67462 | 02. B2B Direct Through Reseller | 67507 | 3. Partner Contracting & Commercial Setup | Medium | Feature 3 activity 3.4; alternative Feature 15 'Customer Contracting & Contract Synchronization with FnO' (contract sync to F&O). | 38:14-38:40, 50:45-51:00, 2:13:47-2:14:19 | Mapped
Support mid-contract list price updates with notice period | 67462 | 02. B2B Direct Through Reseller | 67508 | 4. Commercial Terms Synchronization | Medium | Feature 4 activity 4.1 'Sync Pricing & Discounts' publishes updated pricing to Zinfi. | 2:18:33-2:19:17 | Mapped
Sync approved partner record from Zinfi to CRM only after onboarding is finalized | 67462 | 02. B2B Direct Through Reseller | 67510 | 6. Partner Data Available in CRM & synchronization with FnO | High | Feature 6 input is 'Partner Data Synced from PRM' and activity 6.1 'Partner Data Availability in CRM'. Feature 5 (Onboard Approved Partner) was the alternative. | 21:03-23:45, 24:37-25:31, 36:50-37:19 | Mapped
Scope partner record visibility to originating legal entity | 67462 | 02. B2B Direct Through Reseller | 67510 | 6. Partner Data Available in CRM & synchronization with FnO | Medium | Feature 6 covers partner data availability in CRM; no Feature addresses security scoping directly. | 26:50-29:02 | Mapped
Assign single record owner with legal-entity-wide read visibility | 67462 | 02. B2B Direct Through Reseller | 67510 | 6. Partner Data Available in CRM & synchronization with FnO | Medium | Same data-availability Feature as the sync story; ownership is a property of the synced record. | 29:08-33:19 | Mapped
Enforce read-only partner record with approval-based edit exception | 67462 | 02. B2B Direct Through Reseller | 67510 | 6. Partner Data Available in CRM & synchronization with FnO | Medium | Feature 6 covers partner data in CRM. Decision recorded by facilitator: read-only for everyone for now. | 33:19-40:06 | Mapped
Capture required account-planning data points in CRM | 67462 | 02. B2B Direct Through Reseller | 67510 | 6. Partner Data Available in CRM & synchronization with FnO | Medium | Feature 6 activity 6.2 (partner data made available in CRM) is the closest. Alternative: Feature 1 'Channel Partner Strategy' (Epic 02). Business said no CRM data points were foreseen. | 40:10-44:11 | Mapped
Sync partner training completion status to CRM | 67462 | 02. B2B Direct Through Reseller | 67512 | 7. Partner Training & Enablement | High | Feature 7 activity 7.4 'Track Training Completion' is a direct match. | 24:56-25:31, 3:07:18-3:07:44 | Mapped
Report lead closure outcomes by partner for distributed leads | 67462 | 02. B2B Direct Through Reseller | 67514 | 9. Partner Lead Generation & Performance | Medium | Feature 9 activity 9.3 'Measure Lead Generation Outcomes' and 9.2 'Track Campaign Performance'. | 53:42-53:50, 1:02:51-1:03:28, 1:05:01-1:05:44 | Mapped
Create and distribute leads from CRM to partners via Zinfi | 67462 | 02. B2B Direct Through Reseller | 67515 | 10. Lead Registration & Qualification | Medium | Feature 10 activity 1.3 'Assign or approve lead ownership' fits assignment to partners. Epic 01 Feature 3.1 'Sales Lead Handoff' is direct-sales only. | 49:37-51:04, 58:12-59:35, 3:08:56-3:09:15 | Mapped
Allow account managers to create and maintain their own leads | 67462 | 02. B2B Direct Through Reseller | 67515 | 10. Lead Registration & Qualification | Medium | Same Feature as lead distribution (lead ownership assignment). | 52:08-53:11 | Mapped
Allow partners to optionally register their own leads in Zinfi | 67462 | 02. B2B Direct Through Reseller | 67515 | 10. Lead Registration & Qualification | High | Feature 10 activity 1.1 'Register Partner-Generated Leads' is a direct match. | 51:16-51:52, 59:35-1:01:16 | Mapped
Synchronize leads and opportunities two ways between Zinfi and CRM | 67462 | 02. B2B Direct Through Reseller | 67516 | 11. Opportunity Management | Medium | Feature 11 activity 2.3 'Manage Partner & Sales Collaboration'. Feature 10 was the alternative for lead-only sync. | 57:33-57:48, 1:16:42-1:19:30, 2:11:09-2:12:20 | Mapped
Share opportunity notes and customer communication between partner and Heartstream users | 67462 | 02. B2B Direct Through Reseller | 67516 | 11. Opportunity Management | High | Feature 11 activity 2.3 'Manage Partner & Sales Collaboration' is a direct match. | 55:11-56:56, 1:19:31-1:21:21 | Mapped
Register partner-led opportunities in Zinfi and synchronize them to CRM | 67462 | 02. B2B Direct Through Reseller | 67516 | 11. Opportunity Management | Medium | Feature 11 activity 2.1 'Create & Manage Opportunities'. | 1:01:35-1:05:00, 1:16:42-1:19:30 | Mapped
Import batches of partner opportunities into Zinfi from partner CRM systems | 67462 | 02. B2B Direct Through Reseller | 67516 | 11. Opportunity Management | Medium | Feature 11 activity 2.1 'Create & Manage Opportunities'; Europe-specific requirement. | 44:19-45:20, 1:02:05-1:02:40 | Mapped
Flag an opportunity as a registered deal by product or solution category | 67462 | 02. B2B Direct Through Reseller | 67516 | 11. Opportunity Management | Medium | Feature 11 covers creating and managing opportunities including partner collaboration. | 1:13:14-1:15:08 | Mapped
Prevent duplicate deal registration for the same customer opportunity | 67462 | 02. B2B Direct Through Reseller | 67516 | 11. Opportunity Management | Medium | Feature 11 and Feature 10 both cover registration; Feature 11 chosen as the block applies on opportunity/deal creation. | 1:09:07-1:12:34 | Mapped
Mark individual deals as registered case by case for any product line | 67462 | 02. B2B Direct Through Reseller | 67516 | 11. Opportunity Management | Medium | Feature 11 covers opportunity management; mechanism (checkbox or list) left open by business. | 1:15:08-1:16:22 | Mapped
Show open opportunities and registered deals on the customer account | 67462 | 02. B2B Direct Through Reseller | 67516 | 11. Opportunity Management | Medium | Feature 11 activity 2.2/2.3; Zinfi-registered deals appear against the customer in CRM per facilitator. | 1:07:02-1:08:55 | Mapped
Derive quote pricing from the partner's active contract | 67462 | 02. B2B Direct Through Reseller | 67517 | 12. Quotation & Pricing | High | Feature 12 activity 3.2 'Apply Partner Pricing & Discounts' is a direct match. | 2:04:15-2:04:57, 2:38:10-2:38:39 | Mapped
Route additional discount beyond contract through tiered approval | 67462 | 02. B2B Direct Through Reseller | 67517 | 12. Quotation & Pricing | High | Feature 12 activity 3.4 'Negotiate & Revise Quotations'. Same rule is needed for direct sales (Epic 01 Feature 7); to be reused there. | 2:15:12-2:17:06, 2:34:34-2:38:00 | Mapped
Honor quoted pricing for open quotes through the validity period | 67462 | 02. B2B Direct Through Reseller | 67517 | 12. Quotation & Pricing | Medium | Feature 12 activity 3.4 / 3.5 covers quotation lifecycle. | 2:21:04-2:21:38 | Mapped
Re-trigger approval on pricing or configuration revision, not on date-only changes | 67462 | 02. B2B Direct Through Reseller | 67517 | 12. Quotation & Pricing | High | Feature 12 activity 3.4 'Negotiate & Revise Quotations' is a direct match. | 2:47:19-2:49:51 | Mapped
Request time-bound part-number discounts outside an opportunity | 67462 | 02. B2B Direct Through Reseller | 67519 | 14. Commercial Pricing Management | Medium | Feature 14 activity 5.3 'Maintain Pricing Discounts'. Duplicate Feature titles exist in Epics 01 and 03; resolved by ID within Epic 02. | 2:35:12-2:36:03 | Mapped
Convert an approved quote into an order with last-minute configuration changes | 67462 | 02. B2B Direct Through Reseller | 67521 | 16. Order Capture / Management & Order processing by order sync between F&O and CRM | High | Feature 16 activities 8.1 'Create Customer Order' and 8.2 'Validate Pricing & Entitlements'. | 2:02:23-2:03:25, 2:04:57-2:05:04, 2:43:48-2:44:12 | Mapped
Validate partner purchase-order pricing against contract pricing at order entry | 67462 | 02. B2B Direct Through Reseller | 67521 | 16. Order Capture / Management & Order processing by order sync between F&O and CRM | Medium | Feature 16 activity 8.2 'Validate Pricing & Entitlements'. | 1:59:50-2:00:40, 2:03:25-2:04:15 | Mapped
Place partner orders through the Zinfi portal | 67462 | 02. B2B Direct Through Reseller | 67521 | 16. Order Capture / Management & Order processing by order sync between F&O and CRM | Medium | Feature 16 activity 8.1 'Create Customer Order'; Zinfi order entry stated by UST as most probable path. | 2:09:53-2:12:20, 2:22:15-2:23:51 | Mapped
Require requested delivery date on every order | 67462 | 02. B2B Direct Through Reseller | 67521 | 16. Order Capture / Management & Order processing by order sync between F&O and CRM | High | Feature 16 activity 8.1 'Create Customer Order'. | 2:42:38-2:44:56 | Mapped
Support line-level requested delivery dates for staggered shipments | 67462 | 02. B2B Direct Through Reseller | 67521 | 16. Order Capture / Management & Order processing by order sync between F&O and CRM | Medium | Feature 16 activity 8.1; Europe prefers one RDD per order, North America needs staggered lines. | 2:44:59-2:47:19 | Mapped
Confirm the sales order and transmit it to F&O for fulfillment | 67462 | 02. B2B Direct Through Reseller | 67522 | 17. Sales Order Approval | High | Feature 17 activities 12.2 'Confirm Sales Order' and 11.3 'Submit Sales Order for fulfillment'. | 2:21:45-2:22:15, 2:41:32-2:42:06 | Mapped
Lock order from cancellation and edit after a defined fulfillment status | 67462 | 02. B2B Direct Through Reseller | 67523 | 18. Fulfillment & Shipment | Medium | Feature 18 activity 14.4 'Update Order Status'. | 2:50:06-2:52:52 | Mapped
Show order, shipment and invoice status to partners in Zinfi | 67462 | 02. B2B Direct Through Reseller | 67523 | 18. Fulfillment & Shipment | High | Feature 18 activities 14.2 'Update Shipment Status' and 14.3 'Notify Partner / Customer'. | 2:41:57-2:42:34, 2:52:00-2:52:32 | Mapped
Provide required customs and shipment documents for applicable regions | 67462 | 02. B2B Direct Through Reseller | 67523 | 18. Fulfillment & Shipment | Medium | Feature 18 activity 14.1 'Process Fulfilment & Shipment'. | 2:53:02-2:55:27 | Mapped
Record post-warranty parts coverage against serial numbers for service partners | 67557 | 03. B2B Direct Service & Solution Delivery | 67561 | 3. Service Entitlements | Medium | Feature 3 'Service Entitlements' (3.1 Create Entitlements, 3.2 Link Contract and Assets, 3.4 Track Usage and Validity). Feature 2 'Service Contract Management' was the alternative. | 2:24:25-2:33:33 | Mapped
Create install base record on delivery for serialized hardware | 67557 | 03. B2B Direct Service & Solution Delivery | 67562 | 4. Install Base Management | High | Feature 4 activity 4.1 'Create Installed Products'. Alternative: Epic 01 Feature 15 (14.1 includes Install Base Generation). | 2:55:33-3:05:34 | Mapped
Update current install base location through a quick controlled process | 67557 | 03. B2B Direct Service & Solution Delivery | 67562 | 4. Install Base Management | High | Feature 4 activities 4.2 'Link Account and Locations' and 4.4 'Govern Installed-base quality'. | 2:57:04-2:58:08, 3:06:11-3:06:26 | Mapped
Allow partner-initiated install base change request via Zinfi | 67557 | 03. B2B Direct Service & Solution Delivery | 67562 | 4. Install Base Management | Medium | Feature 4 activity 4.4 'Govern Installed-base quality'. | 3:00:30-3:01:11, 3:06:26-3:06:43 | Mapped
Synchronize partner-raised case escalation from Zinfi to CRM for triage | 67572 | 04. Service Support | 67574 | 1. Case Intake & Classification | High | Epic 04 Feature 1 'Case Intake & Classification' activity 1.2 'Partner/distributor raises request' is a direct match. | 3:07:48-3:08:24 | Mapped