## Test Coverage
Heartstream Greenfield IT — E2E Test Coverage
Execution-ready coverage across all 18 approved future-state business flows
Coverage Metric | Value |  | Execution Metric | Step Count |  | Design Basis
Business processes | 18 |  | Not Run | 259 |  | Case model | 1 positive + 1 key exception/control case per process
Distinct test cases | 36 |  | Pass | 0 |  | Ownership | Swimlane role; ISV ownership aligned to ISV and Purpose
Detailed test steps | 259 |  | Fail / Blocked | 0 |  | Execution | Update Actual Result, Status, Defect ID and Comments in the test register
Scenario ID | Business Process | Positive Case | Exception / Control Case | Detailed Steps | Critical Steps | Primary Systems / ISVs | Source Flow | Coverage Focus
1 | B2B Direct Sales | TC01-P01 | TC01-N01 | 17 | 11 | D365 CE/F&O; SPS Commerce; DHL | 01. B2B Direct Sales v1.1.pdf | Lead-to-contract, order-to-cash, credit and installed base
2 | B2B Through Reseller | TC02-P01 | TC02-N01 | 16 | 11 | Zinfi; D365 CE/F&O; SPS Commerce; DHL | 02. B2B Through Reseller v1.1.pdf | Partner enablement, sale, fulfillment, rebate/MDF
3 | B2B Direct Service & Solution Delivery | TC03-P01 | TC03-N01 | 14 | 14 | D365 Customer Service; Zinfi; Veeva | 03. B2B Direct Service & Solution Delivery V1.1.pdf | Contract, entitlement, case resolution, complaint routing
4 | Service Support | TC04-P01 | TC04-N01 | 14 | 9 | D365 Customer Service; ASP; Veeva | 04. Service Support_V1.1.pdf | Tier 3, root cause, field action and knowledge closure
5 | B2B Service Request (AED) | TC05-P01 | TC05-N01 | 15 | 10 | D365 Customer Service/F&O; DHL; SPS; Veeva | 05. B2B Service Request (AED) v1.1.pdf | Warranty, RMA, replacement, return and failure analysis
6 | B2B Service Support (ALS) | TC06-P01 | TC06-N01 | 13 | 0 | D365 Customer Service/F&O; DHL; ASP | 06. B2B Service Support (ALS).pdf | Spare parts, installation, returns and chargeback
7 | B2C AED Shop | TC07-P01 | TC07-N01 | 13 | 13 | Truvio; Vertex; Commerce HQ; F&O; DHL | 07. B2C AED shop.pdf | Web checkout, payment, tax/address, fulfillment
8 | B2C App Purchase | TC08-P01 | TC08-N01 | 13 | 0 | Copernicus App; Truvio; Commerce HQ; F&O; DHL | 08. B2C app purchase.pdf | Consumable alert, one-click purchase and deferment
9 | Software Upgrade | TC09-P01 | TC09-N01 | 15 | 15 | Copernicus App; D365 CE/F&O; Distribution System | 09. Software upgrade V1.1.pdf | Eligibility, purchase, entitlement, package activation
10 | Auto-renewal Subscription | TC10-P01 | TC10-N01 | 14 | 14 | D365 CE; Commerce HQ; Payment Gateway | 10. Auto-renewal subscription V1.1.pdf | Automated renewal, payment failure and service continuity
11 | Subscription Renewal (Non-auto) | TC11-P01 | TC11-N01 | 12 | 7 | D365 CE; Copernicus App; Truvio | 11. Subscription renewal (non-auto) V1.1.pdf | Customer opt-in renewal and cancellation
12 | Subscription via PO | TC12-P01 | TC12-N01 | 14 | 14 | D365 CE/F&O; Customer Portal | 12. Subscription via PO V1.1.pdf | PO validation, entitlement extension and invoicing
13 | Social Commerce | TC13-P01 | TC13-N01 | 14 | 5 | Zinfi; Social Platform; SPS; DHL; D365 F&O | 13 - Social commerce.pdf | Channel setup, social order, integration recovery, reporting
14 | Affiliates Programs | TC14-P01 | TC14-N01 | 14 | 0 | Zinfi; Truvio; D365 F&O; DHL | 14 - Affiliates Programs.pdf | Affiliate attribution, sale and commission controls
15 | Brick & Mortar Retailers | TC15-P01 | TC15-N01 | 14 | 5 | Zinfi; SPS Commerce; DHL; D365 F&O | 15 - Brick & Mortar Retailers.pdf | Retail onboarding, EDI order and demand planning
16 | Ecommerce (B2B & B2C) | TC16-P01 | TC16-N01 | 14 | 14 | Truvio; Vertex; Commerce HQ; F&O; SPS; DHL | 16. Ecommerce (B2B & B2C).pdf | B2B/B2C channel controls, fulfillment and reporting
17 | Procure to Pay | TC17-P01 | TC17-N01 | 14 | 14 | D365 F&O; SPS Commerce; DHL | 17-Procure to Pay.pdf | Requisition, PO, receipt, match, invoice and payment
18 | New Product to Production | TC18-P01 | TC18-N01 | 19 | 19 | PTC Arena/CAD Talk; D365 F&O; Flex; SPS; DHL; Veeva | 18. New product to production v1.1.pdf | EC, release, cut-in, manufacture, quality and availability

## E2E Test Cases
Heartstream Greenfield IT — End-to-End Test Cases
Scope: 18 future-state business processes ¦ Positive and key control/exception coverage ¦ Step-level owners and systems
Scenario ID | Business Process | Test Case ID | Test Case Title | Test Type | Priority | Preconditions | Step # | Detailed Test Step | Step Owner | Application / ISV | Test Data / Input | Expected Result | Actual Result | Status | Defect ID | Comments
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 1 | Maintain sellable products, base prices and customer-specific trade agreement/discount rules. | Sales / Finance | D365 CE Sales / D365 F&O | AED bundle, service and subscription SKUs | Products and valid commercial rules are available for quoting. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 2 | Aggregate customer data, segment the account, execute a campaign, create and qualify the lead. | Marketing | D365 CE Marketing/Sales | Target account and campaign response | A qualified sales lead is created with complete source and score. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 3 | Hand off the qualified lead, assign ownership and convert it to an opportunity. | Sales Operations | D365 CE Sales | Qualified lead | Sales accepts the lead and an owned opportunity is created. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 4 | Create a quotation with products, services/subscriptions, payment terms and negotiated pricing. | Sales | D365 CE Sales | Customer requirements and pricing rules | Quote totals, discounts, tax basis and terms are correct. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 5 | Obtain customer approval/sign-off and complete quotation approval. | Sales / Customer | D365 CE Sales | Approved quote or customer PO | Approved quotation is locked with approval evidence. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 6 | Create the customer contract, associate sites and terms, onboard the customer and complete credit control. | Sales / Finance | D365 CE / D365 F&O | Approved quote, legal entity, credit data | Active contract and customer account are ready for order processing. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 7 | Capture the customer order and validate availability, compliance and any required approvals. | Retail Operations | D365 Commerce HQ / D365 F&O | Customer order | Validated sales order is confirmed and released for fulfillment. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 8 | Synchronize the order to F&O, SPS Commerce and DHL; return status to CE. | Supply Chain / Customer Operations | SPS Commerce / D365 F&O / DHL | Confirmed sales order | Matching order IDs, quantities and status exist across all systems. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 9 | Pick, ship and deliver the order; update shipment status and notify the customer. | Warehouse / Logistics | DHL / D365 F&O | Released fulfillment order | Delivery confirmation and final order status are recorded. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 10 | Generate and post the invoice, recognize revenue, collect and apply cash. | Finance | D365 F&O | Fulfilled order and payment | Invoice is posted, revenue recognized and receivable settled. |  | Not Run
1 | B2B Direct Sales | TC01-P01 | Direct sale from lead through cash and installed base | Positive E2E | Critical | Products, prices and a creditworthy B2B customer are available; inventory exists. | 11 | Create the installed-base record from the fulfilled order. | Service Operations | D365 CE Customer Service | Delivered serialized device | Installed base contains correct customer, site, serial number and coverage. |  | Not Run
1 | B2B Direct Sales | TC01-N01 | Quote or credit approval exception blocks order release | Negative / Control | High | A quote exceeds approval threshold or customer fails credit policy. | 1 | Create a quote with an out-of-policy discount and submit for approval. | Sales | D365 CE Sales | Discount above approval limit | Quote is routed to the correct approver and cannot be finalized. |  | Not Run
1 | B2B Direct Sales | TC01-N01 | Quote or credit approval exception blocks order release | Negative / Control | High | A quote exceeds approval threshold or customer fails credit policy. | 2 | Reject the quote and record the reason. | Sales Approver | D365 CE Sales | Reject: discount not supported | Quote status becomes rejected and audit history is retained. |  | Not Run
1 | B2B Direct Sales | TC01-N01 | Quote or credit approval exception blocks order release | Negative / Control | High | A quote exceeds approval threshold or customer fails credit policy. | 3 | Revise pricing within policy and resubmit. | Sales | D365 CE Sales | Revised discount | Approval workflow restarts with the revised total. |  | Not Run
1 | B2B Direct Sales | TC01-N01 | Quote or credit approval exception blocks order release | Negative / Control | High | A quote exceeds approval threshold or customer fails credit policy. | 4 | Fail the customer credit check during contract/order readiness. | Finance / Credit Control | D365 F&O | Customer over credit limit | Credit hold is applied and order release is blocked. |  | Not Run
1 | B2B Direct Sales | TC01-N01 | Quote or credit approval exception blocks order release | Negative / Control | High | A quote exceeds approval threshold or customer fails credit policy. | 5 | Approve an authorized exception or reduce exposure and recheck credit. | Finance Approver | D365 F&O | Approved override or payment | Hold is released only with approval evidence. |  | Not Run
1 | B2B Direct Sales | TC01-N01 | Quote or credit approval exception blocks order release | Negative / Control | High | A quote exceeds approval threshold or customer fails credit policy. | 6 | Confirm the order can proceed after both quote and credit approvals. | Retail Operations | D365 F&O | Cleared order | Order is confirmed without bypassing controls. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 1 | Define partner tiers, eligibility, benefits, rebates and MDF framework. | Partner Management | Zinfi | Partner program policy | Active partner program and eligibility rules are available. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 2 | Capture the application, evaluate eligibility and approve enrollment. | Partner Management | Zinfi | New reseller application | Approved partner profile is created. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 3 | Create partner account, contract, pricing, discounts and rebate eligibility. | Partner Management / Finance | Zinfi / D365 F&O | Approved profile and commercial terms | Active partner contract contains correct commercial rules. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 4 | Provision portal credentials, deliver training and record certification. | Partner Management | Zinfi | Partner users and course completion | Partner can access the portal and is marked enabled/certified. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 5 | Synchronize partner profile to D365 CE and F&O and commercial terms back to Zinfi. | Partner Management / Finance | Zinfi / D365 CE / D365 F&O | Active partner account | Partner IDs and terms match in all systems. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 6 | Register and qualify a partner-sourced lead; create the opportunity. | Partner / Sales | Zinfi / D365 CE Sales | Customer lead | Qualified partner lead and opportunity preserve attribution. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 7 | Create and approve a quotation using partner pricing, promotions and terms. | Sales | D365 CE Sales | Partner opportunity | Approved quote uses valid partner entitlements. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 8 | Create customer contract and capture the reseller-linked customer order. | Sales / Partner | D365 CE / Commerce HQ | Approved quote | Customer order retains partner and contract references. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 9 | Validate, synchronize, fulfill and deliver the order. | Retail Operations / Warehouse | D365 F&O / SPS Commerce / DHL | Submitted order | Delivered order and statuses reconcile across systems. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 10 | Post invoice and collect customer payment. | Finance | D365 F&O | Delivery confirmation | Posted invoice and settled receivable are created. |  | Not Run
2 | B2B Through Reseller | TC02-P01 | Reseller onboarding through sale, fulfillment and rebate settlement | Positive E2E | Critical | Partner program, products, prices and rebate rules are configured. | 11 | Calculate, validate, approve and settle rebate/MDF. | Finance / Partner Management | D365 F&O / Zinfi | Eligible transaction and MDF claim | Correct earned rebate/MDF is approved, paid and reported. |  | Not Run
2 | B2B Through Reseller | TC02-N01 | Ineligible partner or invalid rebate claim is rejected | Negative / Control | High | Eligibility and rebate/MDF limits are configured. | 1 | Submit a partner application missing a mandatory eligibility criterion. | Prospective Partner | Zinfi | Incomplete certification or territory conflict | Application is flagged ineligible and is not activated. |  | Not Run
2 | B2B Through Reseller | TC02-N01 | Ineligible partner or invalid rebate claim is rejected | Negative / Control | High | Eligibility and rebate/MDF limits are configured. | 2 | Record rejection and verify no credentials or D365 partner account are provisioned. | Partner Management | Zinfi / D365 CE | Rejected application | No active partner access or downstream account exists. |  | Not Run
2 | B2B Through Reseller | TC02-N01 | Ineligible partner or invalid rebate claim is rejected | Negative / Control | High | Eligibility and rebate/MDF limits are configured. | 3 | For an active partner, submit a rebate/MDF claim outside the eligible period or above limits. | Partner | Zinfi | Invalid claim | Claim is held or rejected with a clear reason. |  | Not Run
2 | B2B Through Reseller | TC02-N01 | Ineligible partner or invalid rebate claim is rejected | Negative / Control | High | Eligibility and rebate/MDF limits are configured. | 4 | Validate the claim against sales attribution, rules and supporting evidence. | Finance | D365 F&O / Zinfi | Claim and transaction history | Ineligible amount is excluded and audit detail is retained. |  | Not Run
2 | B2B Through Reseller | TC02-N01 | Ineligible partner or invalid rebate claim is rejected | Negative / Control | High | Eligibility and rebate/MDF limits are configured. | 5 | Confirm no payout is generated until an authorized correction is approved. | Finance Approver | D365 F&O | Rejected claim | Payment proposal excludes the claim. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 1 | Create service quotation with applicable products, markets, price group and commercial terms. | Service Sales | D365 CE Sales | Service coverage requirement | Service contract quotation is complete and priced correctly. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 2 | Approve and activate the service/partner commercial contract. | Service Sales / Partner Management | D365 CE / Zinfi | Signed contract | Active contract and coverage dates are recorded. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 3 | Register and validate the deal/opportunity, including duplicate check. | Partner / Sales | Zinfi / D365 CE Sales | Partner deal details | Validated deal is linked to account, products and forecast. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 4 | Create or update the installed asset and service entitlement. | Service Operations | D365 CE Customer Service | Device serial and contract | Asset has active coverage and SLA. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 5 | Submit a service request with channel, issue, asset and contract details. | Customer / Partner | Zinfi / Customer Portal | Covered device issue | Request is acknowledged and a case is created. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 6 | Validate entitlement, classify, route and assign the service case. | Customer Service | D365 Customer Service | Service request | Case is routed to the correct queue with SLA timer. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 7 | Investigate, diagnose, communicate updates and record the action plan. | Customer Service | D365 Customer Service | Assigned case | Diagnosis, activity history and action plan are complete. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 8 | Escalate if SLA is at risk and implement the approved resolution. | Customer Service Lead | D365 Customer Service | SLA threshold and action plan | Escalation is visible and resolution is completed. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-P01 | Service contract activation through entitled case closure | Positive E2E | Critical | Service products, prices and a customer/partner account exist. | 9 | Close the case and update SLA, resolution and trend metrics. | Customer Service | D365 Customer Service | Resolved case | Closed case retains resolution, entitlement and performance data. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-N01 | Potential complaint is routed to Veeva and regulatory stakeholders | Negative / Compliance | Critical | Complaint criteria and Veeva integration/routing are configured. | 1 | Submit a service issue containing a potential safety or quality complaint. | Customer / Partner | Customer Portal / Zinfi | Safety-related issue description | Service case is created without losing original details. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-N01 | Potential complaint is routed to Veeva and regulatory stakeholders | Negative / Compliance | Critical | Complaint criteria and Veeva integration/routing are configured. | 2 | Assess complaint criteria during investigation. | Customer Service | D365 Customer Service | Assigned complaint-like case | Case is flagged as a potential complaint. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-N01 | Potential complaint is routed to Veeva and regulatory stakeholders | Negative / Compliance | Critical | Complaint criteria and Veeva integration/routing are configured. | 3 | Create the complaint record in Veeva and transfer required case/asset data. | Customer Service / Quality | Veeva / D365 Customer Service | Case, device serial, patient-safety details | Veeva complaint ID is returned and linked to the service case. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-N01 | Potential complaint is routed to Veeva and regulatory stakeholders | Negative / Compliance | Critical | Complaint criteria and Veeva integration/routing are configured. | 4 | Notify Regulatory/Quality and trigger return or R&D investigation where required. | Quality / Regulatory | Veeva | Complaint record | Correct stakeholders and downstream workflow are engaged. |  | Not Run
3 | B2B Direct Service & Solution Delivery | TC03-N01 | Potential complaint is routed to Veeva and regulatory stakeholders | Negative / Compliance | Critical | Complaint criteria and Veeva integration/routing are configured. | 5 | Verify the service case cannot be closed before required complaint actions are complete. | Customer Service Lead | D365 Customer Service / Veeva | Open regulatory tasks | Closure is blocked or controlled with audit evidence. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 1 | Register the support request, validate installed product and coverage, and create the case. | Customer Service | D365 Customer Service | Customer, asset, issue and entitlement | Service case is complete and eligible for support. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 2 | Assess severity, priority, patient-safety and early-life-failure flags; review knowledge. | Customer Service | D365 Customer Service | Case symptoms and history | Case is correctly classified and routed. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 3 | Assign Tier 3 engineering/product specialist and ownership. | Customer Service Lead | D365 Customer Service | Advanced support case | Tier 3 owner and SLA are set. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 4 | Perform detailed investigation, capture evidence and determine root cause. | Engineering / Product Specialist | D365 Customer Service | Logs, photos and device data | Root cause assessment and evidence are documented. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 5 | Define and approve corrective action and decide that field intervention is required. | Engineering / Customer Service | D365 Customer Service | Root cause and recommendation | Approved resolution specifies work and parts. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 6 | Create work order and hand off asset, issue and action details to the ASP. | Customer Service | D365 Customer Service / D365 F&O | Approved field action | ASP receives an actionable work order. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 7 | Repair, replace, update or correct the device and capture completion evidence. | Authorized Service Provider | ASP / D365 Customer Service | Work order | Execution result and evidence are returned. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 8 | Update installed base/service records and validate the result with the customer. | Customer Service | D365 Customer Service | ASP completion and customer confirmation | Asset history and resolution validation are complete. |  | Not Run
4 | Service Support | TC04-P01 | Tier 3 investigation through ASP corrective service and closure | Positive E2E | Critical | A valid installed asset, entitlement and triaged Tier 1/2 case exist. | 9 | Record root cause, update knowledge and close the case. | Customer Service | D365 Customer Service | Validated resolution | Case closes with reusable knowledge and full audit trail. |  | Not Run
4 | Service Support | TC04-N01 | Unresolved root cause or non-reimbursable ASP work stays controlled | Negative / Control | High | Tier 3 case requires field investigation. | 1 | Complete initial investigation without a confirmed root cause. | Engineering | D365 Customer Service | Insufficient evidence | Case remains open and additional investigation is requested. |  | Not Run
4 | Service Support | TC04-N01 | Unresolved root cause or non-reimbursable ASP work stays controlled | Negative / Control | High | Tier 3 case requires field investigation. | 2 | Create a field investigation work order with required evidence criteria. | Customer Service | D365 Customer Service | Field investigation request | ASP receives scope but no final corrective action authorization. |  | Not Run
4 | Service Support | TC04-N01 | Unresolved root cause or non-reimbursable ASP work stays controlled | Negative / Control | High | Tier 3 case requires field investigation. | 3 | Return an execution result that does not meet evidence or reimbursement requirements. | Authorized Service Provider | ASP / D365 Customer Service | Incomplete work evidence | Work is flagged for review and reimbursement is not approved. |  | Not Run
4 | Service Support | TC04-N01 | Unresolved root cause or non-reimbursable ASP work stays controlled | Negative / Control | High | Tier 3 case requires field investigation. | 4 | Escalate to engineering/quality and define the next corrective action. | Customer Service Lead | D365 Customer Service / Veeva if complaint | Failed validation | Escalation and revised action are documented. |  | Not Run
4 | Service Support | TC04-N01 | Unresolved root cause or non-reimbursable ASP work stays controlled | Negative / Control | High | Tier 3 case requires field investigation. | 5 | Verify case closure is blocked until customer validation and required records are complete. | Customer Service Lead | D365 Customer Service | Open tasks | Case remains open with SLA/escalation status visible. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 1 | Distributor submits warranty request with serial, failure details and documents. | Distributor | Zinfi / B2C Portal | Defective AED/accessory | Request is acknowledged with complete evidence. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 2 | Review account, installed device, coverage and entitlement; approve warranty. | Customer Service | D365 Customer Service | Warranty request | Warranty authorization is recorded. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 3 | Create RMA and replacement/return order and send request to F&O. | Customer Service | D365 Customer Service / D365 F&O | Approved warranty | Linked RMA and replacement order are created. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 4 | Validate and reserve inventory and release the order. | Warehouse / Supply Chain | D365 F&O | Replacement SKU | Inventory is reserved and fulfillment order released. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 5 | Pick, pack, ship and generate tracking through DHL/SPS. | Warehouse / Logistics | DHL / SPS Commerce | Released replacement order | Tracking is synchronized and customer/distributor notified. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 6 | Confirm replacement delivery and update warranty case/RMA. | Customer Service | D365 Customer Service | Delivery confirmation | Replacement is marked delivered. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 7 | Receive, inspect and process the returned defective device. | Warehouse / Logistics | DHL / D365 F&O | RMA return | Return receipt and inspection are recorded. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 8 | Dispatch defective device to the failure-analysis lab and confirm receipt. | Logistics / R&D | DHL / R&D Lab | Returned serialized device | Chain of custody and lab receipt are recorded. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 9 | Perform failure/root-cause analysis and record reason code. | R&D / Failure Analysis Lab | R&D Lab / Veeva | Defective device | Analysis result and failure code are available. |  | Not Run
5 | B2B Service Request (AED) | TC05-P01 | AED warranty replacement, return, failure analysis and closure | Positive E2E | Critical | Distributor account, serialized device, active warranty and replacement stock exist. | 10 | Close warranty transactions and linked Veeva case where applicable. | Customer Service / Quality | D365 Customer Service / Veeva | Completed return and analysis | Warranty and quality records close with traceability. |  | Not Run
5 | B2B Service Request (AED) | TC05-N01 | Warranty rejection or replacement backorder is handled | Negative / Exception | High | Use an expired warranty or unavailable replacement SKU. | 1 | Submit a replacement request for a device outside warranty or entitlement. | Distributor | Zinfi / B2C Portal | Expired coverage | Request reaches warranty validation. |  | Not Run
5 | B2B Service Request (AED) | TC05-N01 | Warranty rejection or replacement backorder is handled | Negative / Exception | High | Use an expired warranty or unavailable replacement SKU. | 2 | Reject the request and record the policy reason; verify no replacement order is created. | Customer Service | D365 Customer Service / D365 F&O | Ineligible request | Distributor is notified and no fulfillment transaction exists. |  | Not Run
5 | B2B Service Request (AED) | TC05-N01 | Warranty rejection or replacement backorder is handled | Negative / Exception | High | Use an expired warranty or unavailable replacement SKU. | 3 | Repeat with an eligible device but zero replacement inventory. | Customer Service | D365 Customer Service / D365 F&O | Eligible serial, unavailable SKU | Approved warranty order is placed on backorder. |  | Not Run
5 | B2B Service Request (AED) | TC05-N01 | Warranty rejection or replacement backorder is handled | Negative / Exception | High | Use an expired warranty or unavailable replacement SKU. | 4 | Verify procurement/replenishment is triggered and customer receives revised timing. | Supply Chain | D365 F&O | Backordered item | Supply action and notification are recorded. |  | Not Run
5 | B2B Service Request (AED) | TC05-N01 | Warranty rejection or replacement backorder is handled | Negative / Exception | High | Use an expired warranty or unavailable replacement SKU. | 5 | Confirm shipment proceeds only after inventory becomes available and reservation succeeds. | Warehouse | D365 F&O / DHL | Replenished stock | Order releases without duplicate shipment. |  | Not Run
6 | B2B Service Support (ALS) | TC06-P01 | ALS spare-parts diagnosis, fulfillment, installation and return | Positive E2E | High | ASP is active; device, entitlement and spare-part inventory exist. | 1 | Diagnose the device issue and identify required spare parts and warranty scenario. | Authorized Service Provider | ASP Portal / D365 Customer Service | ALS device symptoms | Required part and chargeability are determined. |  | Not Run
6 | B2B Service Support (ALS) | TC06-P01 | ALS spare-parts diagnosis, fulfillment, installation and return | Positive E2E | High | ASP is active; device, entitlement and spare-part inventory exist. | 2 | Create and submit the spare-parts order request. | Authorized Service Provider | ASP Portal | Part, quantity and device serial | Request is submitted with case reference. |  | Not Run
6 | B2B Service Support (ALS) | TC06-P01 | ALS spare-parts diagnosis, fulfillment, installation and return | Positive E2E | High | ASP is active; device, entitlement and spare-part inventory exist. | 3 | Validate warranty/entitlement and create the spare-parts sales order. | Service Operations / Sales | D365 Customer Service / D365 F&O | Order request | Eligible order and pricing/chargeback treatment are correct. |  | Not Run
6 | B2B Service Support (ALS) | TC06-P01 | ALS spare-parts diagnosis, fulfillment, installation and return | Positive E2E | High | ASP is active; device, entitlement and spare-part inventory exist. | 4 | Check inventory, allocate parts and release for fulfillment. | Warehouse | D365 F&O | Spare-parts sales order | Inventory is reserved and order released. |  | Not Run
6 | B2B Service Support (ALS) | TC06-P01 | ALS spare-parts diagnosis, fulfillment, installation and return | Positive E2E | High | ASP is active; device, entitlement and spare-part inventory exist. | 5 | Pick, pack, ship and update tracking. | Warehouse / Logistics | D365 F&O / DHL | Released order | ASP receives tracking and confirmed delivery. |  | Not Run
6 | B2B Service Support (ALS) | TC06-P01 | ALS spare-parts diagnosis, fulfillment, installation and return | Positive E2E | High | ASP is active; device, entitlement and spare-part inventory exist. | 6 | Install the part and verify the device works. | Authorized Service Provider | ASP Portal / D365 Customer Service | Delivered spare part | Resolution and installed part serial/lot are recorded. |  | Not Run
6 | B2B Service Support (ALS) | TC06-P01 | ALS spare-parts diagnosis, fulfillment, installation and return | Positive E2E | High | ASP is active; device, entitlement and spare-part inventory exist. | 7 | Create a return request for unused/defective part where applicable. | Authorized Service Provider | ASP Portal / D365 F&O | Returnable spare part | Eligible RMA is generated. |  | Not Run
6 | B2B Service Support (ALS) | TC06-P01 | ALS spare-parts diagnosis, fulfillment, installation and return | Positive E2E | High | ASP is active; device, entitlement and spare-part inventory exist. | 8 | Receive and process the return and close all transactions. | Warehouse / Finance | D365 F&O | Returned part | Inventory/financial treatment and return closure are correct. |  | Not Run
6 | B2B Service Support (ALS) | TC06-N01 | Out-of-warranty spare part creates correct chargeback | Negative / Commercial | High | Device entitlement is expired and chargeable pricing is configured. | 1 | Submit a spare-parts request for an out-of-warranty device. | Authorized Service Provider | ASP Portal | Expired device coverage | Request is flagged as chargeable. |  | Not Run
6 | B2B Service Support (ALS) | TC06-N01 | Out-of-warranty spare part creates correct chargeback | Negative / Commercial | High | Device entitlement is expired and chargeable pricing is configured. | 2 | Review eligibility and present/assign the correct chargeback scenario. | Service Operations | D365 Customer Service / D365 F&O | Part and account pricing | Charge and approval requirement are calculated. |  | Not Run
6 | B2B Service Support (ALS) | TC06-N01 | Out-of-warranty spare part creates correct chargeback | Negative / Commercial | High | Device entitlement is expired and chargeable pricing is configured. | 3 | Decline the charge and verify no inventory is released. | Authorized Service Provider | ASP Portal | Declined quote | Order is cancelled/held and inventory remains available. |  | Not Run
6 | B2B Service Support (ALS) | TC06-N01 | Out-of-warranty spare part creates correct chargeback | Negative / Commercial | High | Device entitlement is expired and chargeable pricing is configured. | 4 | Approve the charge and resubmit. | Authorized Service Provider | ASP Portal | Approved charge | Sales order becomes eligible for fulfillment. |  | Not Run
6 | B2B Service Support (ALS) | TC06-N01 | Out-of-warranty spare part creates correct chargeback | Negative / Commercial | High | Device entitlement is expired and chargeable pricing is configured. | 5 | Fulfill, invoice and verify the financial posting references the service case. | Warehouse / Finance | D365 F&O / DHL | Approved chargeable order | Shipment and invoice post once with correct account/amount. |  | Not Run
7 | B2C AED Shop | TC07-P01 | Consumer AED webstore purchase through revenue recognition | Positive E2E | Critical | Sellable AED inventory, tax/address rules and credit-card test account exist. | 1 | Access the e-shop, register/login, browse AEDs/accessories and add items to cart. | Customer | Truvio - B2C (ECom) | Consumer and product selections | Cart contains correct SKUs, prices and quantities. |  | Not Run
7 | B2C AED Shop | TC07-P01 | Consumer AED webstore purchase through revenue recognition | Positive E2E | Critical | Sellable AED inventory, tax/address rules and credit-card test account exist. | 2 | Review cart, enter delivery address and validate address/tax. | Customer | Truvio / Vertex | Valid deliverable address | Address is accepted and indirect tax is calculated correctly. |  | Not Run
7 | B2C AED Shop | TC07-P01 | Consumer AED webstore purchase through revenue recognition | Positive E2E | Critical | Sellable AED inventory, tax/address rules and credit-card test account exist. | 3 | Complete credit-card payment and create the eCommerce order. | Customer | Truvio / Payment Gateway | Approved test card | Single paid order and confirmation are created. |  | Not Run
7 | B2C AED Shop | TC07-P01 | Consumer AED webstore purchase through revenue recognition | Positive E2E | Critical | Sellable AED inventory, tax/address rules and credit-card test account exist. | 4 | Synchronize order to Commerce HQ and D365 F&O. | Retail Operations | Truvio / D365 Commerce HQ / D365 F&O | Paid eCommerce order | Order IDs, totals, tax and customer data reconcile. |  | Not Run
7 | B2C AED Shop | TC07-P01 | Consumer AED webstore purchase through revenue recognition | Positive E2E | Critical | Sellable AED inventory, tax/address rules and credit-card test account exist. | 5 | Validate and confirm the sales order; submit fulfillment request. | Retail Operations / Sales | D365 F&O | Received order | Order is released only after validation. |  | Not Run
7 | B2C AED Shop | TC07-P01 | Consumer AED webstore purchase through revenue recognition | Positive E2E | Critical | Sellable AED inventory, tax/address rules and credit-card test account exist. | 6 | Synchronize to SPS/DHL, fulfill, ship and update tracking/status. | Warehouse / Logistics | SPS Commerce / DHL | Released order | Shipment and status updates return to source systems. |  | Not Run
7 | B2C AED Shop | TC07-P01 | Consumer AED webstore purchase through revenue recognition | Positive E2E | Critical | Sellable AED inventory, tax/address rules and credit-card test account exist. | 7 | Notify the customer and confirm delivery. | Warehouse / Customer Operations | Truvio / DHL | Tracking and delivery | Customer sees final delivery status. |  | Not Run
7 | B2C AED Shop | TC07-P01 | Consumer AED webstore purchase through revenue recognition | Positive E2E | Critical | Sellable AED inventory, tax/address rules and credit-card test account exist. | 8 | Generate/post invoice and recognize revenue. | Finance | D365 F&O | Delivered order | Invoice and revenue equal the paid order, including tax. |  | Not Run
7 | B2C AED Shop | TC07-N01 | Invalid address or declined card prevents duplicate order | Negative / Control | Critical | Invalid address and declined-card test data are available. | 1 | Enter an invalid or unsupported delivery address at checkout. | Customer | Truvio / Vertex | Invalid postal address | Address error is shown and order cannot be submitted. |  | Not Run
7 | B2C AED Shop | TC07-N01 | Invalid address or declined card prevents duplicate order | Negative / Control | Critical | Invalid address and declined-card test data are available. | 2 | Correct the address and verify tax is recalculated. | Customer | Truvio / Vertex | Valid corrected address | New tax and total are displayed before payment. |  | Not Run
7 | B2C AED Shop | TC07-N01 | Invalid address or declined card prevents duplicate order | Negative / Control | Critical | Invalid address and declined-card test data are available. | 3 | Submit payment using a declined card. | Customer | Truvio / Payment Gateway | Declined test card | Payment fails and no confirmed order is sent downstream. |  | Not Run
7 | B2C AED Shop | TC07-N01 | Invalid address or declined card prevents duplicate order | Negative / Control | Critical | Invalid address and declined-card test data are available. | 4 | Retry with an approved card. | Customer | Truvio / Payment Gateway | Approved test card | Exactly one paid order is created. |  | Not Run
7 | B2C AED Shop | TC07-N01 | Invalid address or declined card prevents duplicate order | Negative / Control | Critical | Invalid address and declined-card test data are available. | 5 | Verify Commerce HQ/F&O contain no duplicate or unpaid sales order. | Retail Operations | D365 Commerce HQ / D365 F&O | Customer checkout reference | Only the successful order is present. |  | Not Run
8 | B2C App Purchase | TC08-P01 | Copernicus consumables alert through purchase and fulfillment | Positive E2E | High | Registered device has pads/battery approaching replacement; product stock exists. | 1 | Monitor device consumable status and identify replacement need. | Service Operations | Copernicus App | Device usage/replacement cycle | Eligible pads/battery are identified. |  | Not Run
8 | B2C App Purchase | TC08-P01 | Copernicus consumables alert through purchase and fulfillment | Positive E2E | High | Registered device has pads/battery approaching replacement; product stock exists. | 2 | Notify the consumer and display recommended compatible products. | Service Operations | Copernicus App | Registered device model | App shows correct replacement SKU and timing. |  | Not Run
8 | B2C App Purchase | TC08-P01 | Copernicus consumables alert through purchase and fulfillment | Positive E2E | High | Registered device has pads/battery approaching replacement; product stock exists. | 3 | Customer selects Buy Now; auto-add recommended item and optional accessories. | Customer | Copernicus App / Truvio | Recommendation | Cart has compatible items and correct quantities. |  | Not Run
8 | B2C App Purchase | TC08-P01 | Copernicus consumables alert through purchase and fulfillment | Positive E2E | High | Registered device has pads/battery approaching replacement; product stock exists. | 4 | Review cart, capture delivery details and process payment. | Customer | Copernicus App / Truvio / Payment Gateway | Valid address and card | Paid eCommerce replacement order is created. |  | Not Run
8 | B2C App Purchase | TC08-P01 | Copernicus consumables alert through purchase and fulfillment | Positive E2E | High | Registered device has pads/battery approaching replacement; product stock exists. | 5 | Synchronize order to Commerce HQ and D365 F&O. | Retail Operations | D365 Commerce HQ / D365 F&O | App order | Order values and device/customer references reconcile. |  | Not Run
8 | B2C App Purchase | TC08-P01 | Copernicus consumables alert through purchase and fulfillment | Positive E2E | High | Registered device has pads/battery approaching replacement; product stock exists. | 6 | Validate, confirm and release the order for fulfillment. | Retail Operations / Sales | D365 F&O | Received order | Confirmed order is ready for shipment. |  | Not Run
8 | B2C App Purchase | TC08-P01 | Copernicus consumables alert through purchase and fulfillment | Positive E2E | High | Registered device has pads/battery approaching replacement; product stock exists. | 7 | Fulfill, ship, update status and notify customer in app/email. | Warehouse / Logistics | SPS Commerce / DHL / Copernicus App | Released order | Customer receives tracking and delivery confirmation. |  | Not Run
8 | B2C App Purchase | TC08-P01 | Copernicus consumables alert through purchase and fulfillment | Positive E2E | High | Registered device has pads/battery approaching replacement; product stock exists. | 8 | Post invoice and recognize revenue. | Finance | D365 F&O | Delivered order | Financial postings equal the order and payment. |  | Not Run
8 | B2C App Purchase | TC08-N01 | Consumer defers reminder and no order is created | Negative / Alternate | Medium | Replacement recommendation is active. | 1 | Display the consumable replacement notification. | Service Operations | Copernicus App | Eligible device alert | Recommendation and Buy Now option are visible. |  | Not Run
8 | B2C App Purchase | TC08-N01 | Consumer defers reminder and no order is created | Negative / Alternate | Medium | Replacement recommendation is active. | 2 | Customer declines Buy Now or defers the reminder. | Customer | Copernicus App | Defer selection | No cart checkout or order is created. |  | Not Run
8 | B2C App Purchase | TC08-N01 | Consumer defers reminder and no order is created | Negative / Alternate | Medium | Replacement recommendation is active. | 3 | Verify reminder preference and next trigger are stored. | Service Operations | Copernicus App | Deferred alert | Reminder is rescheduled according to rule. |  | Not Run
8 | B2C App Purchase | TC08-N01 | Consumer defers reminder and no order is created | Negative / Alternate | Medium | Replacement recommendation is active. | 4 | Confirm no order, payment, invoice or fulfillment transaction exists. | Retail Operations / Finance | Truvio / D365 F&O | Device/customer reference | Downstream systems remain unchanged. |  | Not Run
8 | B2C App Purchase | TC08-N01 | Consumer defers reminder and no order is created | Negative / Alternate | Medium | Replacement recommendation is active. | 5 | At the next trigger, verify the recommendation reappears without duplication. | Service Operations | Copernicus App | Next reminder date | Single current reminder is shown. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 1 | Identify upgrade-eligible devices and present options, benefits and supported devices. | Service Operations | Copernicus App | Installed base and device configuration | Only compatible upgrades are offered. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 2 | Select upgrade features and target devices and add upgrade to cart. | Customer | Copernicus App | Eligible devices | Upgrade cart contains correct feature/device scope. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 3 | Review details and complete payment or approved PO checkout. | Customer | Copernicus App / Truvio | Approved card or PO | Paid/approved upgrade order is created. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 4 | Create and synchronize software/hardware upgrade order to Commerce HQ, F&O and CRM. | Retail Operations | D365 Commerce HQ / D365 F&O / D365 CE | Upgrade order | Order IDs, devices and value reconcile. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 5 | Validate order, create entitlement and confirm purchase. | Retail Operations / Service Operations | D365 F&O / D365 CE | Validated order | Active entitlement is linked to customer and devices. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 6 | Generate upgrade work order and sales order. | Service Operations / Finance | D365 CE / D365 F&O | Active entitlement | Work order and sales order reference the entitlement. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 7 | Publish package and authorize download. | Software Distribution | Software Distribution System | Work order and package | Correct signed package is available to target devices. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 8 | Download, install and activate the upgrade. | Customer / Device | Copernicus App / Device | Authorized package | Upgrade completes and device reports active version. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 9 | Notify customer, update upgrade history and installed base. | Service Operations | Copernicus App / D365 CE | Activation confirmation | Installed base/version and customer history are updated. |  | Not Run
9 | Software Upgrade | TC09-P01 | Eligible software upgrade purchase, entitlement and device activation | Positive E2E | Critical | Eligible installed device, compatible package and payment/PO route exist. | 10 | Post invoice, recognize revenue and collect/apply cash for PO route. | Finance | D365 F&O | Completed upgrade order | Financial treatment is correct for payment method. |  | Not Run
9 | Software Upgrade | TC09-N01 | Ineligible or failed upgrade does not activate entitlement incorrectly | Negative / Control | Critical | Use an unsupported device or simulate installation failure. | 1 | Attempt to select an upgrade for an unsupported device. | Customer | Copernicus App | Incompatible device/version | Selection is blocked with compatibility reason. |  | Not Run
9 | Software Upgrade | TC09-N01 | Ineligible or failed upgrade does not activate entitlement incorrectly | Negative / Control | Critical | Use an unsupported device or simulate installation failure. | 2 | Verify no paid order or entitlement is created for the blocked selection. | Service Operations | D365 CE / D365 F&O | Blocked attempt | No downstream transaction exists. |  | Not Run
9 | Software Upgrade | TC09-N01 | Ineligible or failed upgrade does not activate entitlement incorrectly | Negative / Control | Critical | Use an unsupported device or simulate installation failure. | 3 | For an eligible device, purchase the upgrade and simulate download/install failure. | Customer / Device | Copernicus App / Software Distribution System | Corrupt or interrupted installation | Failure is logged and device remains on prior working version. |  | Not Run
9 | Software Upgrade | TC09-N01 | Ineligible or failed upgrade does not activate entitlement incorrectly | Negative / Control | Critical | Use an unsupported device or simulate installation failure. | 4 | Verify entitlement remains valid for retry but completion status is not set. | Service Operations | D365 CE | Failed activation | Entitlement and work order show pending/failed, not completed. |  | Not Run
9 | Software Upgrade | TC09-N01 | Ineligible or failed upgrade does not activate entitlement incorrectly | Negative / Control | Critical | Use an unsupported device or simulate installation failure. | 5 | Retry with valid package and confirm one successful activation/history entry. | Software Distribution / Customer | Software Distribution System / Copernicus App | Valid package | Upgrade completes without duplicate billing or entitlement. |  | Not Run
10 | Auto-renewal Subscription | TC10-P01 | Auto-renewal from trigger through uninterrupted service | Positive E2E | Critical | Active subscription has auto-renewal enabled and a valid payment method. | 1 | Review active terms and identify the subscription by expiry/reorder/replacement trigger. | Service Operations | D365 CE | Active auto-renew subscription | Subscription is selected once as a renewal candidate. |  | Not Run
10 | Auto-renewal Subscription | TC10-P01 | Auto-renewal from trigger through uninterrupted service | Positive E2E | Critical | Active subscription has auto-renewal enabled and a valid payment method. | 2 | Send expiry notice with renewal terms, pricing and required regulatory information. | Retail Operations | D365 CE / Copernicus App | Renewal candidate | Customer receives complete notice within the configured lead time. |  | Not Run
10 | Auto-renewal Subscription | TC10-P01 | Auto-renewal from trigger through uninterrupted service | Positive E2E | Critical | Active subscription has auto-renewal enabled and a valid payment method. | 3 | Initiate renewal based on hardware, consumables, service/software line composition. | Retail Operations | D365 CE / Commerce HQ | Subscription components | Renewal order contains all eligible lines and dates. |  | Not Run
10 | Auto-renewal Subscription | TC10-P01 | Auto-renewal from trigger through uninterrupted service | Positive E2E | Critical | Active subscription has auto-renewal enabled and a valid payment method. | 4 | Process stored payment and confirm transaction. | Retail Operations / Customer | Commerce HQ / Payment Gateway | Valid payment token | Single successful charge and renewal order are recorded. |  | Not Run
10 | Auto-renewal Subscription | TC10-P01 | Auto-renewal from trigger through uninterrupted service | Positive E2E | Critical | Active subscription has auto-renewal enabled and a valid payment method. | 5 | Synchronize and validate the renewal order in Commerce HQ. | Retail Operations | D365 Commerce HQ | Renewal sales order | Validated order reconciles to subscription and payment. |  | Not Run
10 | Auto-renewal Subscription | TC10-P01 | Auto-renewal from trigger through uninterrupted service | Positive E2E | Critical | Active subscription has auto-renewal enabled and a valid payment method. | 6 | Create/activate renewal entitlement and extend coverage period. | Service Operations | D365 CE | Validated renewal order | New entitlement begins without overlap gap or duplicate term. |  | Not Run
10 | Auto-renewal Subscription | TC10-P01 | Auto-renewal from trigger through uninterrupted service | Positive E2E | Critical | Active subscription has auto-renewal enabled and a valid payment method. | 7 | Update subscription status and maintain remote service access. | Service Operations | D365 CE / Remote Connectivity Platform | Renewed entitlement | Connectivity remains uninterrupted. |  | Not Run
10 | Auto-renewal Subscription | TC10-P01 | Auto-renewal from trigger through uninterrupted service | Positive E2E | Critical | Active subscription has auto-renewal enabled and a valid payment method. | 8 | Display/send confirmation and update subscription history. | Customer Operations | Copernicus App / Email / D365 CE | Active renewed subscription | Customer and audit history show the new term. |  | Not Run
10 | Auto-renewal Subscription | TC10-N01 | Auto-renewal payment failure places renewal on hold | Negative / Control | Critical | Auto-renewal is enabled but payment method will be declined. | 1 | Trigger renewal and send the pre-renewal notification. | Service Operations | D365 CE / Copernicus App | Expiring subscription | Customer is notified before charge attempt. |  | Not Run
10 | Auto-renewal Subscription | TC10-N01 | Auto-renewal payment failure places renewal on hold | Negative / Control | Critical | Auto-renewal is enabled but payment method will be declined. | 2 | Attempt renewal payment using declined/expired payment token. | Retail Operations | Payment Gateway / Commerce HQ | Declined payment token | Payment fails and no active renewal is posted. |  | Not Run
10 | Auto-renewal Subscription | TC10-N01 | Auto-renewal payment failure places renewal on hold | Negative / Control | Critical | Auto-renewal is enabled but payment method will be declined. | 3 | Place subscription renewal on hold/deferred and notify customer. | Service Operations | D365 CE / Copernicus App | Payment failure | Status, reason and retry instructions are visible. |  | Not Run
10 | Auto-renewal Subscription | TC10-N01 | Auto-renewal payment failure places renewal on hold | Negative / Control | Critical | Auto-renewal is enabled but payment method will be declined. | 4 | Verify entitlement is not extended beyond authorized grace policy. | Service Operations | D365 CE | Failed renewal | Access follows configured grace/termination rule. |  | Not Run
10 | Auto-renewal Subscription | TC10-N01 | Auto-renewal payment failure places renewal on hold | Negative / Control | Critical | Auto-renewal is enabled but payment method will be declined. | 5 | Update payment method and retry once. | Customer | Copernicus App / Payment Gateway | Valid replacement method | One successful renewal is created without duplicate charge. |  | Not Run
10 | Auto-renewal Subscription | TC10-N01 | Auto-renewal payment failure places renewal on hold | Negative / Control | Critical | Auto-renewal is enabled but payment method will be declined. | 6 | If customer cancels, send cancellation/service termination notice and stop future retries. | Customer Operations | D365 CE / Copernicus App | Cancellation selection | Auto-renew flag is off and termination date is recorded. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-P01 | Customer-initiated renewal through payment and service continuity | Positive E2E | Critical | Active non-auto subscription is approaching expiry. | 1 | Identify the expiring non-auto subscription using configured triggers. | Service Operations | D365 CE | Active subscription | Subscription appears once in renewal candidates. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-P01 | Customer-initiated renewal through payment and service continuity | Positive E2E | Critical | Active non-auto subscription is approaching expiry. | 2 | Send renewal notice and present term, price and cancellation options. | Retail Operations | D365 CE / Copernicus App | Renewal candidate | Customer can review accurate renewal choices. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-P01 | Customer-initiated renewal through payment and service continuity | Positive E2E | Critical | Active non-auto subscription is approaching expiry. | 3 | Customer accepts, reviews renewal details and proceeds to checkout. | Customer | Copernicus App / Truvio | Selected term | Checkout references the correct subscription. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-P01 | Customer-initiated renewal through payment and service continuity | Positive E2E | Critical | Active non-auto subscription is approaching expiry. | 4 | Process payment and confirm the transaction. | Customer / Retail Operations | Payment Gateway / Commerce HQ | Approved card | Payment confirmation and renewal order are created. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-P01 | Customer-initiated renewal through payment and service continuity | Positive E2E | Critical | Active non-auto subscription is approaching expiry. | 5 | Create subscription order, synchronize to Commerce HQ and validate details. | Retail Operations | D365 Commerce HQ | Renewal transaction | Validated order matches selected term and payment. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-P01 | Customer-initiated renewal through payment and service continuity | Positive E2E | Critical | Active non-auto subscription is approaching expiry. | 6 | Extend entitlement, update subscription and maintain service access. | Service Operations | D365 CE | Validated confirmed order | New term is active with no service gap. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-P01 | Customer-initiated renewal through payment and service continuity | Positive E2E | Critical | Active non-auto subscription is approaching expiry. | 7 | Send confirmation and update subscription history. | Customer Operations | Copernicus App / Email / D365 CE | Active subscription | Customer and audit records show renewal. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-N01 | Customer cancellation stops renewal and terminates service correctly | Negative / Alternate | High | Non-auto subscription renewal notice has been sent. | 1 | Open the renewal notice and select cancellation instead of renewal. | Customer | Copernicus App | Expiring subscription | Cancellation confirmation is requested. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-N01 | Customer cancellation stops renewal and terminates service correctly | Negative / Alternate | High | Non-auto subscription renewal notice has been sent. | 2 | Confirm cancellation and capture reason/effective date. | Customer | Copernicus App / D365 CE | Cancellation choice | Renewal decision is recorded as cancelled. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-N01 | Customer cancellation stops renewal and terminates service correctly | Negative / Alternate | High | Non-auto subscription renewal notice has been sent. | 3 | Verify no checkout, payment or renewal order is created. | Retail Operations | Commerce HQ / D365 F&O | Subscription reference | No financial or order transaction exists. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-N01 | Customer cancellation stops renewal and terminates service correctly | Negative / Alternate | High | Non-auto subscription renewal notice has been sent. | 4 | End entitlement/service on the correct contract date. | Service Operations | D365 CE / Remote Connectivity Platform | Cancellation effective date | Access remains through allowed term and then terminates. |  | Not Run
11 | Subscription Renewal (Non-auto) | TC11-N01 | Customer cancellation stops renewal and terminates service correctly | Negative / Alternate | High | Non-auto subscription renewal notice has been sent. | 5 | Send cancellation and service termination notice and update history. | Customer Operations | Copernicus App / Email / D365 CE | Terminated subscription | Customer receives notice and history is auditable. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 1 | Monitor terms, identify expiring subscription and verify PO eligibility. | Service Operations | D365 CE | PO-billable customer/subscription | Eligible renewal candidate is created. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 2 | Send expiry notification and present PO renewal option. | Retail Operations | D365 CE / Customer Portal | Renewal candidate | Customer sees correct term and PO route. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 3 | Select renewal term, create request and submit PO details/document. | Customer | Customer Portal | Valid PO number, amount and document | Submitted PO is linked to the subscription. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 4 | Receive sales order request and validate PO, subscription, amount and customer authority. | Retail Operations | D365 CE / D365 F&O | Submitted PO | Order is approved and customer is notified. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 5 | Synchronize approved sales order to D365 F&O. | Retail Operations | D365 CE / D365 F&O | Approved order | Order values and PO reference reconcile. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 6 | Create renewal work order, link approved order and initiate entitlement renewal. | Service Operations | D365 CE | Approved sales order | Renewal workflow references the PO/order. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 7 | Extend entitlement and maintain remote connectivity. | Service Operations | D365 CE / Remote Connectivity Platform | Renewal initiated | Subscription is active for the new period. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 8 | Generate/send customer invoice and update billing status. | Finance | D365 F&O | Approved fulfilled renewal | Invoice carries correct PO number and terms. |  | Not Run
12 | Subscription via PO | TC12-P01 | Subscription renewal by approved purchase order | Positive E2E | Critical | Customer is eligible for PO billing and has an expiring subscription. | 9 | Send confirmation and update subscription history. | Customer Operations | D365 CE / Email | Active subscription | Customer sees active renewal and invoice reference. |  | Not Run
12 | Subscription via PO | TC12-N01 | Invalid or over-value PO is rejected without entitlement extension | Negative / Control | Critical | Use an invalid PO number or amount below renewal value. | 1 | Submit renewal request with invalid, duplicate or insufficient-value PO. | Customer | Customer Portal | Invalid PO | Request is received but not approved. |  | Not Run
12 | Subscription via PO | TC12-N01 | Invalid or over-value PO is rejected without entitlement extension | Negative / Control | Critical | Use an invalid PO number or amount below renewal value. | 2 | Validate PO and reject/return it with a specific reason. | Retail Operations / Finance | D365 CE / D365 F&O | Submitted PO | Order decision is rejected and customer is notified. |  | Not Run
12 | Subscription via PO | TC12-N01 | Invalid or over-value PO is rejected without entitlement extension | Negative / Control | Critical | Use an invalid PO number or amount below renewal value. | 3 | Verify no sales order is synchronized and no invoice is issued. | Finance | D365 F&O | Rejected request | No posting or billing transaction exists. |  | Not Run
12 | Subscription via PO | TC12-N01 | Invalid or over-value PO is rejected without entitlement extension | Negative / Control | Critical | Use an invalid PO number or amount below renewal value. | 4 | Verify entitlement is not extended and connectivity follows expiry/grace policy. | Service Operations | D365 CE | Rejected renewal | Subscription status is not falsely active. |  | Not Run
12 | Subscription via PO | TC12-N01 | Invalid or over-value PO is rejected without entitlement extension | Negative / Control | Critical | Use an invalid PO number or amount below renewal value. | 5 | Resubmit a corrected PO and confirm the controlled approval flow restarts. | Customer / Retail Operations | Customer Portal / D365 CE | Corrected PO | New version is approved with audit history preserved. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 1 | Define social-commerce strategy, target platform, assortment and governance. | Partner Management | Zinfi | Approved channel business case | Channel strategy and operating model are documented. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 2 | Recruit platform/partner, agree commercial terms and configure integrations. | Partner Management | Zinfi / Social Platform | Partner and agreement | Active social-commerce channel is created. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 3 | Onboard partner, publish catalog/content and enable promotions. | Partner Management / Marketing | Zinfi / Social Platform | Catalog and campaign assets | Partner can sell approved products at correct prices. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 4 | Execute campaign/influencer activity and track qualified demand. | Marketing | Social Platform / Zinfi | Campaign and MDF plan | Traffic and conversion attribution are captured. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 5 | Customer discovers product and places an order on the channel. | Customer | Social Commerce Platform | Product, address, payment | eCommerce order contains customer and channel attribution. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 6 | Synchronize to Commerce HQ/F&O; validate, confirm and release order. | Retail Operations / Sales | D365 Commerce HQ / D365 F&O | Channel order | Order is confirmed with correct totals and source. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 7 | Send order to SPS/DHL, fulfill, ship and synchronize status to CE/app. | Warehouse / Logistics | SPS Commerce / DHL / D365 CE | Released order | Delivery and status updates reconcile. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 8 | Invoice and recognize revenue. | Finance | D365 F&O | Delivered order | Invoice and revenue are posted correctly. |  | Not Run
13 | Social Commerce | TC13-P01 | Social channel setup through customer order and performance reporting | Positive E2E | High | Target platform, products, inventory and commercial model are approved. | 9 | Capture demand signals, forecast/WoC, reviews and platform performance. | SCM / Marketing | D365 F&O / Social Platform | Sales, inventory and engagement data | Forecast and performance reporting include the transaction. |  | Not Run
13 | Social Commerce | TC13-N01 | Channel order integration failure is recovered without duplication | Negative / Integration | Critical | A valid social order exists; integration failure can be simulated. | 1 | Place a valid order on the social platform. | Customer | Social Commerce Platform | Paid order | Source order is confirmed once. |  | Not Run
13 | Social Commerce | TC13-N01 | Channel order integration failure is recovered without duplication | Negative / Integration | Critical | A valid social order exists; integration failure can be simulated. | 2 | Interrupt synchronization to Commerce HQ/F&O. | Customer Operations | Integration / Commerce HQ | Source order ID | Failure is logged and order is not silently lost. |  | Not Run
13 | Social Commerce | TC13-N01 | Channel order integration failure is recovered without duplication | Negative / Integration | Critical | A valid social order exists; integration failure can be simulated. | 3 | Verify fulfillment is blocked while downstream validation is absent. | Retail Operations | D365 F&O | Missing downstream order | No warehouse release occurs. |  | Not Run
13 | Social Commerce | TC13-N01 | Channel order integration failure is recovered without duplication | Negative / Integration | Critical | A valid social order exists; integration failure can be simulated. | 4 | Replay/retry the integration after correcting the issue. | Supply Chain / Customer Operations | SPS Commerce / Integration | Original source order ID | One downstream order is created with original attribution. |  | Not Run
13 | Social Commerce | TC13-N01 | Channel order integration failure is recovered without duplication | Negative / Integration | Critical | A valid social order exists; integration failure can be simulated. | 5 | Complete fulfillment and verify one invoice, one shipment and reconciled status. | Warehouse / Finance | D365 F&O / DHL | Recovered order | No duplicate financial or logistics transaction exists. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 1 | Define affiliate types, eligibility, commission model and governance. | Partner Management | Zinfi | Affiliate program policy | Approved program and commission rules are active. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 2 | Recruit affiliate, validate eligibility, execute contract and activate relationship. | Partner Management | Zinfi | Affiliate application | Active contracted affiliate exists. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 3 | Provision affiliate ID/link/promo code and marketing assets. | Partner Management / Marketing | Zinfi / Truvio | Affiliate account | Tracking identifiers and approved content are usable. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 4 | Publish affiliate promotions and drive traffic to the e-shop. | Marketing / Affiliate | Zinfi / Truvio | Campaign and promo code | Visit and lead carry affiliate attribution. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 5 | Customer purchases through affiliate link/code. | Customer | Truvio - B2C (ECom) | Affiliate-attributed cart | Order records affiliate, promotion and price correctly. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 6 | Synchronize, validate, confirm and fulfill the order. | Retail Operations / Warehouse | Commerce HQ / D365 F&O / SPS / DHL | Paid affiliate order | Delivered order preserves affiliate reference. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 7 | Post invoice and recognize revenue. | Finance | D365 F&O | Delivered order | Revenue is posted once and links to order. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 8 | Verify conversion and commission-eligible transaction in affiliate reporting. | Partner Management / Finance | Zinfi / D365 F&O | Delivered non-returned sale | Correct affiliate and commission basis are reported. |  | Not Run
14 | Affiliates Programs | TC14-P01 | Affiliate activation, attributed sale and commission-ready reporting | Positive E2E | High | Affiliate strategy, commission rules, products and inventory exist. | 9 | Update forecasting, customer voice and platform performance metrics. | SCM / Marketing | D365 F&O / Truvio | Sales and review data | Reporting includes attributed demand and outcomes. |  | Not Run
14 | Affiliates Programs | TC14-N01 | Invalid affiliate code or returned order excludes commission | Negative / Control | High | Use expired promo code and a returnable affiliate order. | 1 | Attempt checkout with expired or unauthorized affiliate code. | Customer | Truvio / Zinfi | Expired code | Discount/attribution is rejected with clear message. |  | Not Run
14 | Affiliates Programs | TC14-N01 | Invalid affiliate code or returned order excludes commission | Negative / Control | High | Use expired promo code and a returnable affiliate order. | 2 | Complete purchase without a valid code and verify no false affiliate attribution. | Customer | Truvio | Standard checkout | Order has no affiliate commission basis. |  | Not Run
14 | Affiliates Programs | TC14-N01 | Invalid affiliate code or returned order excludes commission | Negative / Control | High | Use expired promo code and a returnable affiliate order. | 3 | Create a valid affiliate order and then process a full return/cancellation. | Customer Operations | Truvio / D365 F&O | Returned affiliate order | Order status and revenue reversal are recorded. |  | Not Run
14 | Affiliates Programs | TC14-N01 | Invalid affiliate code or returned order excludes commission | Negative / Control | High | Use expired promo code and a returnable affiliate order. | 4 | Recalculate affiliate eligibility after the return. | Finance / Partner Management | D365 F&O / Zinfi | Returned transaction | Commission amount is zero/reversed per policy. |  | Not Run
14 | Affiliates Programs | TC14-N01 | Invalid affiliate code or returned order excludes commission | Negative / Control | High | Use expired promo code and a returnable affiliate order. | 5 | Confirm reporting retains the event and exclusion reason for audit. | Partner Management | Zinfi | Commission adjustment | Affiliate report shows excluded/reversed status, not deletion. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 1 | Define retail channel strategy, target segments, pricing and promotion approach. | Partner Management | Zinfi | Retail business case | Approved channel strategy is documented. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 2 | Evaluate retailer, negotiate terms and execute contract. | Partner Management / Finance | Zinfi / D365 F&O | Retailer application | Active contract with discounts and terms exists. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 3 | Onboard account, share catalog/pricing and complete retailer training. | Partner Management | Zinfi | Executed contract | Retailer is enabled to transact. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 4 | Execute co-marketing/MDF campaign and generate demand. | Marketing | Zinfi | Campaign plan | Qualified retailer demand is tracked. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 5 | Capture retailer/customer order through channel/EDI. | Retailer / Customer Operations | SPS Commerce | Valid EDI order | Order is acknowledged with correct retailer identifiers. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 6 | Synchronize to Commerce HQ/F&O; validate, confirm and release. | Retail Operations / Sales | SPS Commerce / D365 F&O | EDI sales order | Order data and pricing reconcile. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 7 | Fulfill through DHL and return shipment/status messages. | Warehouse / Logistics | DHL / SPS Commerce | Released order | Retailer receives delivery and EDI status confirmation. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 8 | Invoice and recognize revenue. | Finance | D365 F&O | Delivered order | Invoice uses retailer terms and revenue posts. |  | Not Run
15 | Brick & Mortar Retailers | TC15-P01 | Retailer onboarding through EDI order, delivery and demand planning | Positive E2E | High | Retail strategy, retailer candidate, catalog, terms and stock exist. | 9 | Capture sales/inventory signals and update forecast and weeks of coverage. | SCM | D365 F&O / SPS Commerce | Retail sales and inventory data | Demand forecast and WoC reflect actual activity. |  | Not Run
15 | Brick & Mortar Retailers | TC15-N01 | Invalid EDI order is rejected and corrected cleanly | Negative / Integration | Critical | EDI validation rules and a malformed order are available. | 1 | Transmit an EDI order with invalid item, duplicate PO or missing required data. | Retailer | SPS Commerce | Malformed EDI order | Validation rejects/holds the order with reason. |  | Not Run
15 | Brick & Mortar Retailers | TC15-N01 | Invalid EDI order is rejected and corrected cleanly | Negative / Integration | Critical | EDI validation rules and a malformed order are available. | 2 | Verify no confirmed F&O sales order or fulfillment request is created. | Retail Operations | SPS Commerce / D365 F&O | Rejected message ID | Downstream processing is blocked. |  | Not Run
15 | Brick & Mortar Retailers | TC15-N01 | Invalid EDI order is rejected and corrected cleanly | Negative / Integration | Critical | EDI validation rules and a malformed order are available. | 3 | Send functional/business error acknowledgement to retailer. | Customer Operations | SPS Commerce | Validation errors | Retailer receives actionable rejection detail. |  | Not Run
15 | Brick & Mortar Retailers | TC15-N01 | Invalid EDI order is rejected and corrected cleanly | Negative / Integration | Critical | EDI validation rules and a malformed order are available. | 4 | Correct and retransmit using the same business PO with proper version/control. | Retailer | SPS Commerce | Corrected EDI order | One valid sales order is created. |  | Not Run
15 | Brick & Mortar Retailers | TC15-N01 | Invalid EDI order is rejected and corrected cleanly | Negative / Integration | Critical | EDI validation rules and a malformed order are available. | 5 | Complete fulfillment and reconcile EDI status, shipment and invoice. | Warehouse / Finance | D365 F&O / DHL / SPS Commerce | Corrected order | No duplicate order, shipment or invoice exists. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 1 | Define B2B/B2C channel strategy, operating model, objectives and growth plan. | Partner Management | Zinfi | Approved eCommerce plan | Channel scope and governance are approved. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 2 | Recruit partners, negotiate terms and execute channel contracts. | Partner Management / Finance | Zinfi / D365 F&O | Partner candidates | Active partner contracts and pricing exist. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 3 | Onboard partners, publish catalogs/pricing/assets and enable selling. | Partner Management / Marketing | Zinfi / Truvio | Catalog and accounts | Approved assortments are available by customer type. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 4 | Execute campaigns and generate channel demand. | Marketing | Truvio / Zinfi | B2B/B2C campaigns | Source and conversion data are captured. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 5 | Place representative B2B and B2C orders with correct customer-specific rules. | Customer / Partner | Truvio - B2C (ECom) / B2B Portal | B2B account and B2C consumer | Orders apply correct pricing, tax and identity rules. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 6 | Synchronize to Commerce HQ/F&O; validate and confirm each order. | Retail Operations | D365 Commerce HQ / D365 F&O | eCommerce orders | Orders reconcile and are ready for fulfillment. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 7 | Fulfill through SPS/DHL and synchronize status. | Warehouse / Logistics | SPS Commerce / DHL | Released orders | Delivery status reaches customer-facing channels. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 8 | Invoice and recognize revenue for both customer types. | Finance | D365 F&O | Delivered orders | Correct financial postings occur for B2B and B2C. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-P01 | B2B/B2C commerce channel order through reporting | Positive E2E | Critical | Channel partners, B2B/B2C catalogs, prices and inventory are configured. | 9 | Update forecasting, WoC, customer voice and platform performance. | SCM / Marketing | D365 F&O / Truvio | Sales/inventory/review data | Integrated reporting covers both channel segments. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-N01 | B2B pricing and B2C tax/address rules remain segregated | Negative / Control | Critical | B2B contract price and B2C consumer tax/address rules differ. | 1 | Log in as B2B buyer and verify contract pricing and account terms. | B2B Customer | B2B Portal / D365 F&O | Contracted account | B2B price and terms are applied. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-N01 | B2B pricing and B2C tax/address rules remain segregated | Negative / Control | Critical | B2B contract price and B2C consumer tax/address rules differ. | 2 | Attempt to use B2B-only price/discount in a guest B2C checkout. | B2C Customer | Truvio | B2C guest cart | Unauthorized B2B pricing is not exposed. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-N01 | B2B pricing and B2C tax/address rules remain segregated | Negative / Control | Critical | B2B contract price and B2C consumer tax/address rules differ. | 3 | Enter invalid B2C address and verify Vertex validation/tax control. | B2C Customer | Truvio / Vertex | Invalid address | Checkout is blocked until address is corrected. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-N01 | B2B pricing and B2C tax/address rules remain segregated | Negative / Control | Critical | B2B contract price and B2C consumer tax/address rules differ. | 4 | Submit both valid orders and inspect downstream customer/account classification. | Retail Operations | Commerce HQ / D365 F&O | Valid B2B and B2C orders | Each order posts to the correct customer type and tax treatment. |  | Not Run
16 | Ecommerce (B2B & B2C) | TC16-N01 | B2B pricing and B2C tax/address rules remain segregated | Negative / Control | Critical | B2B contract price and B2C consumer tax/address rules differ. | 5 | Confirm fulfillment/invoicing does not mix terms, prices or addresses. | Warehouse / Finance | D365 F&O / DHL | Two delivered orders | Separate accurate invoices and shipments are produced. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 1 | Identify demand from MRP/min-max/manual need and create purchase requisition lines. | Requester | D365 F&O | Item, quantity, site and need date | Complete requisition is created. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 2 | Submit requisition and obtain approval. | Requester / Approver | D365 F&O | Purchase requisition | Approved requisition retains workflow history. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 3 | Run RFQ if required, select bid and create PO with charges and tax. | Procurement | D365 F&O | Approved requisition and vendor bids | Correct vendor and PO commercial terms are selected. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 4 | Approve/confirm PO and send it to vendor via SPS/DHL integration. | Procurement | D365 F&O / SPS Commerce / DHL | Approved PO | Vendor receives one confirmed PO. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 5 | Register arrival, validate ASN and post product receipt. | Warehouse | DHL / SPS Commerce / D365 F&O | Vendor shipment and ASN | Receipt matches PO and updates on-hand inventory. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 6 | Register vendor invoice and perform two-way/three-way match. | Accounts Payable | D365 F&O | Invoice, PO and receipt | Invoice falls within tolerance and is approved. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 7 | Post the vendor invoice. | Accounts Payable | D365 F&O | Approved matched invoice | Vendor liability and expense/inventory entries post correctly. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 8 | Create payment proposal, approve payment method and generate EFT/ISO 20022 payment. | Finance | D365 F&O / Bank | Due approved invoice | Approved payment file/journal is created. |  | Not Run
17 | Procure to Pay | TC17-P01 | Purchase requisition through three-way match and payment | Positive E2E | Critical | Vendor, item, tax, workflow, bank and matching tolerances are configured. | 9 | Settle transaction and verify P2P completion. | Finance | D365 F&O | Posted payment | Vendor invoice is settled and audit trail is complete. |  | Not Run
17 | Procure to Pay | TC17-N01 | Invoice mismatch or quality failure prevents payment | Negative / Control | Critical | PO, receipt and invoice can be created outside tolerance; quality hold is enabled. | 1 | Receive goods that fail quality inspection or differ from PO quantity. | Warehouse / Quality | D365 F&O | Nonconforming or short shipment | Inventory is held/returned and discrepancy is recorded. |  | Not Run
17 | Procure to Pay | TC17-N01 | Invoice mismatch or quality failure prevents payment | Negative / Control | Critical | PO, receipt and invoice can be created outside tolerance; quality hold is enabled. | 2 | Register vendor invoice with price/quantity outside matching tolerance. | Accounts Payable | D365 F&O | Mismatched invoice | Invoice is placed on hold and cannot post. |  | Not Run
17 | Procure to Pay | TC17-N01 | Invoice mismatch or quality failure prevents payment | Negative / Control | Critical | PO, receipt and invoice can be created outside tolerance; quality hold is enabled. | 3 | Verify payment proposal excludes the held invoice. | Finance | D365 F&O | Held invoice | No payment is generated. |  | Not Run
17 | Procure to Pay | TC17-N01 | Invoice mismatch or quality failure prevents payment | Negative / Control | Critical | PO, receipt and invoice can be created outside tolerance; quality hold is enabled. | 4 | Resolve through vendor return, corrected receipt/invoice or authorized exception. | Procurement / AP / Quality | D365 F&O / SPS Commerce | Resolution evidence | PO/receipt/invoice are corrected with audit trail. |  | Not Run
17 | Procure to Pay | TC17-N01 | Invoice mismatch or quality failure prevents payment | Negative / Control | Critical | PO, receipt and invoice can be created outside tolerance; quality hold is enabled. | 5 | Re-run matching and post/pay only after approval and quality release. | Accounts Payable / Finance | D365 F&O | Resolved transaction | Invoice posts and settles once. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 1 | Initiate engineering change; update requirements, drawings, designs and BOM in PLM. | Engineering / Product Management | PTC Arena/CAD Talk | Approved change request | Controlled product configuration and EC record are created. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 2 | Release prototype, review manufacturing documents and assess production/cut-in impacts. | Engineering / Manufacturing | PTC Arena/CAD Talk | Prototype and manufacturing package | Readiness gaps and impact assessment are documented. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 3 | Approve manufacturing package, send to Flex and resolve CM feedback. | Engineering / Contract Manufacturer | PTC Arena/CAD Talk / Flex | Drawings, BOM, work instructions and tests | Flex accepts a controlled production package. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 4 | Route EC for cross-functional approval, define effectivity/cut-in and close implementation. | Product Release Board / Quality | PTC Arena/CAD Talk / Veeva | EC package and approvals | Approved EC has controlled effectivity and audit trail. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 5 | Synchronize released product master/BOM to D365 F&O and maintain variants/cost/sourcing. | Product Management / SCM | PTC Arena/CAD Talk / D365 F&O | Released PLM data | Production-ready product/BOM is accurate in F&O. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 6 | Assess inventory disposition, regulatory/compliance, supplier, costing and supply risk. | SCM / Quality / Regulatory | D365 F&O / Veeva | Old/new inventory and supplier data | Approved cut-in and disposition strategy are recorded. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 7 | Activate product, BOM and routing; update sourcing and process obsolete/restricted stock. | SCM | D365 F&O | Approved release/effectivity | New version is production-active on the correct date. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 8 | Forecast demand, run master planning, create procurement plan and confirm material/capacity. | Demand Planning / Procurement | D365 F&O | Demand, inventory and capacity | Manufacturing-ready supply plan is approved. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 9 | Create PO/production orders and exchange data with Flex via SPS Commerce. | Procurement / Manufacturing | D365 F&O / SPS Commerce / Flex | Approved BOM and production demand | Flex receives correct version, quantities and test requirements. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 10 | Manufacture, test, package, report completion and release quality order. | Contract Manufacturer / Quality | Flex / Veeva | Production order and test plan | Conforming finished goods and traceability records exist. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 11 | Create ASN and deliver finished goods to DHL; validate PO/item/qty/tracking and post receipt. | Flex / Warehouse | SPS Commerce / DHL / D365 F&O | ASN and finished goods | On-hand, PO status and serial/lot data update correctly. |  | Not Run
18 | New Product to Production | TC18-P01 | Engineering change through Flex manufacture and DHL availability | Positive E2E | Critical | Approved product/change request, design inputs and governance roles exist. | 12 | Release available inventory and fulfill/distribute product. | Warehouse / Logistics | DHL / D365 F&O | Quality-released inventory | Product is available for sales/planning and shipment. |  | Not Run
18 | New Product to Production | TC18-N01 | Cut-in conflict or nonconforming stock is quarantined and reworked | Negative / Compliance | Critical | Old BOM has open PO quantity or received stock fails quality. | 1 | Activate new BOM version with effective cut-in while an old-version PO has remaining quantity. | SCM / Engineering | D365 F&O / PTC Arena | Old PO and approved new BOM | System identifies overlap and requires disposition decision. |  | Not Run
18 | New Product to Production | TC18-N01 | Cut-in conflict or nonconforming stock is quarantined and reworked | Negative / Compliance | Critical | Old BOM has open PO quantity or received stock fails quality. | 2 | Review PO execution state and choose deliver remainder, cancel quantity or create new PO for new BOM. | Procurement / SCM | D365 F&O | Open PO line | Approved decision updates the correct PO/version without ambiguity. |  | Not Run
18 | New Product to Production | TC18-N01 | Cut-in conflict or nonconforming stock is quarantined and reworked | Negative / Compliance | Critical | Old BOM has open PO quantity or received stock fails quality. | 3 | Receive a lot with GIDR/discrepancy or quality failure at DHL. | Warehouse / Quality | DHL / SPS Commerce / D365 F&O | Nonconforming ASN/lot | Stock is segregated to quarantine/blocked and not saleable. |  | Not Run
18 | New Product to Production | TC18-N01 | Cut-in conflict or nonconforming stock is quarantined and reworked | Negative / Compliance | Critical | Old BOM has open PO quantity or received stock fails quality. | 4 | Log GIDR, capture traceability and perform rework/relabel/repackage. | DHL / Contract Manufacturer | DHL SeLECT / Flex | Held serial/lot | Rework evidence and inventory status are controlled. |  | Not Run
18 | New Product to Production | TC18-N01 | Cut-in conflict or nonconforming stock is quarantined and reworked | Negative / Compliance | Critical | Old BOM has open PO quantity or received stock fails quality. | 5 | Re-inspect against QC criteria and obtain QMS release approval. | Quality | Veeva / D365 F&O | Reworked stock and test results | Only passing stock is approved for release. |  | Not Run
18 | New Product to Production | TC18-N01 | Cut-in conflict or nonconforming stock is quarantined and reworked | Negative / Compliance | Critical | Old BOM has open PO quantity or received stock fails quality. | 6 | Send rework confirmation/inventory movement via SPS and update D365 status. | Supply Chain / Customer Operations | SPS Commerce / DHL / D365 F&O | Approved movement advice | Batch/serial/expiry and audit trail reconcile. |  | Not Run
18 | New Product to Production | TC18-N01 | Cut-in conflict or nonconforming stock is quarantined and reworked | Negative / Compliance | Critical | Old BOM has open PO quantity or received stock fails quality. | 7 | Verify failed stock remains quarantined or is scrapped and cannot be fulfilled. | Warehouse / Quality | D365 F&O / DHL | Failed stock | Availability excludes nonconforming inventory. |  | Not Run

## ISV and Purpose (hidden)
ISV / Integration Apps | Typical Business Owner
EDI Vendor | Supply Chain / Customer Operations
(SPS Commerce)
DHL | Logistics / Supply Chain partner
PTC Arena/CAD Talk | Product Management / Engineering / PLM tool
Zinfi | Channel Sales / Partner Management/Possibly B2B direct and indirect sales interface
Deel | Human Resources Application
Veeva | Quality docs, traininng and compliance product
Vertex (D365-Indirect tax) | Tax Calc / Address validation
Navan | Travel & Expense
Truvio - B2C (ECom) | B2C sales Webstore