## UserStories
ID | Work Item Type | Title | Description | Task Type1 | MoM updated and attached | Action items identified and Tasks created | Related Feature identified and linked in ADO | SOW Annexure ID identified | Annexure ID1 | Data Migration needs identified and Tasks created | Area Path | Start Date | Acceptance Criteria | Fit Gap Status
| Workshop | 02. Finance - General Ledger UST Led Workshop - 28/Sep/2026 | Finance and Operations process-modeling workshop for Dynamics 365 Finance general ledger: F&O navigation; chart of accounts and main accounts; financial dimensions (business unit, profit center, cost center); fiscal calendar and ledger period control; currencies and revaluation overview; account structures and advanced rules. Accrual/deferral management and ledger allocations were deferred to a follow-up session. | [7 empty] | Day 2\Business E2E flow | 28-09-2026 08:00
67461 | Epic | 01. B2B Direct Sales | This process illustrates the end-to-end B2B Direct Sales journey, spanning customer acquisition, sales conversion, order execution, fulfilment, financial processing, and installed base creation within the Heartstream ecosystem
67462 | Epic | 02. B2B Direct Through Reseller | This process illustrates the end-to-end reseller sales lifecycle, from partner recruitment and enablement through customer acquisition, sales execution, fulfilment, financial processing, and rebate settlement
67557 | Epic | 03. B2B Direct Service & Solution Delivery
67607 | Epic | 07. B2C AED Shop
67635 | Epic | 09. Software Upgrade
67650 | Epic | 10. Auto-renewal Subscription
67660 | Epic | 11. Subscription Renewal (Non-Auto)
67669 | Epic | 12. Subscription via PO
67482 | Feature | 1. Customer Data & Segmentation | Input: Multi-Source Customer & Engagement Data Activities : 1.1 - Aggregate Cust Data 1.2 - Build Customer Profiles 1.3 - Segment Customers Output: Target Customer Segments
67500 | Feature | 16. Invoicing | Input: Fulfilled Order / Installed Base Record Activities : 15.1 Generate Customer Invoice 15.2 Post Invoice 15.3 Update Billing Status Output: Posted Customer Invoice
67502 | Feature | 18 Cash Collection | Input: Posted Customer Invoice Activities : 17.1 Process Customer Payments 17.2 Apply Payments to Invoices 17.3 Manage Receivables & Collections Output: Cash Collected & Receivables Settled
67489 | Feature | 4. Opportunity Management | Input: Sales Accepted Leads Activities : 4.1 Create Opportunities 4.2 Manage Sales Pipeline 4.3 Track Sales Activities 4.4 Identify Upsell/Cross-Sell Opportunities 4.5 Manage Sales Forecast / Forecast Categories/ Win Lost Analysis 4.6 Review Sales Analytics & Forecast Reports Output: Qualified Sales Opportunities
67490 | Feature | 5. Product & Pricing Management | Input: Product Catalog & Pricing Policies Activities : 5.1 Maintain Products 5.2 Manage Selling Prices Output: Products & Base Pricing Available for Sales
67491 | Feature | 6. Commercial Pricing Management | Commercial Pricing Management Input: Product Catalog & Pricing Policies Activities : 6.1 Maintain Trade Agreement 6.2 Manage Cust Groups 6.3 Maintain Pricing Discounts Output: Customer-Specific Pricing & Discount Rules
67494 | Feature | 9. Contract Management | Input: Customer Approved Quotation Activities : 9.1 Create Customer Contracts 9.2 Manage Commercial Agreements 9.3 Associate Contract Terms & Pricing 9.4 Associate multiple customer sites Output: Active Customer Contract & Contract Pricing Terms
67520 | Feature | 15. Customer Contracting & Contract Synchronization with FnO | Customer Contracting Input: Customer Approved Quotation Activities : 6.1 Create Customer Contract 6.2 Associate Partner Commercial Terms 6.3 Finalize Contractual Agreements Output: Active Customer Contract & Commercial Terms Contract Synchronization Input: Active Customer Contract & Commercial Terms Activities : A.1 Synchronize Contract Details to D365 F&O Output: Contract Synced with F&O
67506 | Feature | 2. Partner Onboarding & Qualification | Input: Partner Program Framework & Channel Policies Activities : 2.1 Capture Partner Applications 2.2 Evaluate Partner Eligibility 2.3 Approve Partner Enrollment Output: Approved Partner Profile
67525 | Feature | 20. Payment Collection | Input: Posted Customer Invoice Activities : 14.1Process Customer Payments 14.2Apply Payments Against Invoices 14.3Manage Receivables & Collections Output: Payment Collected & Receivables Settled
67507 | Feature | 3. Partner Contracting & Commercial Setup | Input: Partner Program Framework & Channel Policies Activities : 3.1 Create Partner Account 3.2 Define Partner Pricing & Discounts 3.3 Define Rebate Eligibility & Rules 3.4 Establish Partner Agreements Output: Active Partner Contract & Commercial Terms
67509 | Feature | 5. Partner Onboarding & Enablement with Partner data synchronization | Input: Partner Program Framework & Channel Policies Activities : 5.1 Onboard Approved Partner 5.2 Provision Partner Access 5.3 Setup Partner Credentials Output: Active Partner Account & Portal Acces
67510 | Feature | 6. Partner Data Available in CRM & synchronization with FnO | Input: Partner Data Synced from PRM Activities : 6.1 Partner Data Availability in CRM 6.2 Partner Data (Status/ Health/Score/Training / complaince / engagement / trends) made avaialable 6.3 Sync Partner Data with F&O Output: Partner Data Available in D365 CE Input: Active Partner Account in CE Activities : B.1 Sync Partner Profile with F&O B.2 Sync Partner Account Information with F&O Output: Partner Data Available in D365 F&O
67511 | Feature | 6.1 Partner Data Available in F&O | Input: Partner Data synced from CE Activities : 6.1 Partner Data Avl in F&O Output: Updated Partner Commercial Data F&O
67514 | Feature | 9. Partner Lead Generation & Performance | Input: Partner-Generated Leads & Campaign Engagement Data Activities : 9.1 Generate Partner-Sourced Leads 9.2 Track Campaign Performance 9.3 Measure Lead Generation Outcomes Output: Qualified Partner-Sourced Leads
67560 | Feature | 2. Service Contract Management | Input: Approved Service Quotation Activities: 2.1 Create Service Contract, 2.2 Define Service Levels, 2.3 Link Customer and locations, 2.4 Maintain Lifecycle and renewals Output: Active Service Contract
67562 | Feature | 4. Install Base Management | Input: Customer, Location and Asset data Activities: 4.1 Create Installed Products, 4.2 Link Account and Locations, 4.3 Maintain warranty and serial data, 4.4 Govern Installed-base quality Output: Trusted Installed Base record
67563 | Feature | 5. Product & Pricing Management | Input: Product Catalog & Pricing Policies Activities: 5.1 Maintain Products, 5.2 Manage Selling Prices Output: Products & Base Pricing Available for Sales
67564 | Feature | 6. Commercial Pricing Management | Input: Product Catalog & Pricing Policies Activities: 6.1 Maintain Trade Agreement, 6.2 Manage Cust Groups, 6.3 Maintain Pricing Discounts Output: Customer-Specific Pricing & Discount Rules
67610 | Feature | 2. Cart & Checkout | Input: Items added to cart Activities: 2.1 Review & Update Cart, 2.2 Checkout & Enter Address Details, 2.3 Process Payment, 2.4 Create Order Maintain Order History Output: eCommerce order created
67643 | Feature | 7. Sales Order Synchronization (Finance) | Input: Upgrade Work Order & Sales Order Created Activities: 7.1 Create Software Upgrade, 7.2 Sales Order, 7.3 Synchronize Sales Order to D365 F&O Output: Software Upgrade Sales Order Available in D365 F&O
67658 | Feature | 6. Entitlement Renewal (D365 CE) | Input: Upgrade Activated Activities: 6.1 Extend entitlement period, 6.2 Update subscription status, 6.3 Maintain service access Output: Active Subscription
67665 | Feature | 4. Order Processing (Retail Operations) | Input: Renewal Order Activities: 4.1 Create Subscription order, 4.2 Sync order to Commerce HQ, 4.3 Validate renewal order details, 4.4 Confirm Renewal Transaction Output: Validated & Confirmed order
67667 | Feature | 5. Entitlement Renewal (D365 CE) | Input: Upgrade Activated Activities: 5.1 Extend entitlement period, 5.2 Update subscription status, 5.3 Maintain service access Output: Active Subscription
67676 | Feature | 6. Entitlement Extension | Input: Renewal Initiated Activities: 6.1 Extend entitlement period, 6.2 Update subscription status, 6.3 Maintain remote connectivity Output: Active Connectivity
67560 | User Story | Configure a global chart of accounts shared across legal entities | As a chief accountant, I need to configure a single global chart of accounts in Dynamics 365 Finance that is shared across all Heartstream legal entities, so that GL account definitions stay consistent for consolidation and group reporting. | [9 empty] | - One chart of accounts is defined and associated with all in-scope legal entities - Main accounts in active use from the Heartstream COA extract are loaded for cutover (not the full legacy Philips catalog) - Legal entities can post to the shared COA subject to account-level restrictions configured per entity
| User Story | Restrict selected main accounts to designated legal entities | As a financial controller, I need to restrict specific main accounts to designated legal entities (for example KPNC or region-specific tax accounts), so that sensitive or statutory accounts are not mis-posted in other company codes. | [9 empty] | - Main accounts identified as legal-entity-specific cannot be selected on transactions in other legal entities - US holding-company-only accounts (for example KPNC reporting) are limited to the US holding legal entity - India GST or other region-specific tax accounts are limited to the India legal entity pending tax workshop confirmation (DQ-GL-003)
67489 | User Story | Map main account categories for out-of-box financial reporting | As a management reporting lead, I need to map main accounts to D365 main account categories that align with Heartstream financial statement groupings, so that standard financial reports can be used with minimal customization. | [9 empty] | - Each active main account is assigned a main account type and main account category - Category mapping supports balance sheet and P&L groupings equivalent to financial statement item and reporting item hierarchies from consolidation - Gaps between Philips POCA/FS item groupings and D365 categories are documented for offline mapping workshops
67510 | User Story | Suspend unused legacy main accounts after cutover | As a chief accountant, I need to suspend main accounts that exist only for legacy SAP manual/automated duplication but are not required in D365, so that the active COA stays manageable without losing one-to-one cutover mapping initially. | [9 empty] | - At cutover, in-use main accounts from Heartstream are imported with a one-to-one match to current SAP usage - Main accounts not required in D365 can be marked suspended so they cannot be used on new transactions - A later cleanup phase can retire suspended accounts without breaking opening-balance migration
67658 | User Story | Suspend unused legacy main accounts after cutover | As a chief accountant, I need to suspend main accounts that exist only for legacy SAP manual/automated duplication but are not required in D365, so that the active COA stays manageable without losing one-to-one cutover mapping initially. | [9 empty] | - At cutover, in-use main accounts from Heartstream are imported with a one-to-one match to current SAP usage - Main accounts not required in D365 can be marked suspended so they cannot be used on new transactions - A later cleanup phase can retire suspended accounts without breaking opening-balance migration
67667 | User Story | Suspend unused legacy main accounts after cutover | As a chief accountant, I need to suspend main accounts that exist only for legacy SAP manual/automated duplication but are not required in D365, so that the active COA stays manageable without losing one-to-one cutover mapping initially. | [9 empty] | - At cutover, in-use main accounts from Heartstream are imported with a one-to-one match to current SAP usage - Main accounts not required in D365 can be marked suspended so they cannot be used on new transactions - A later cleanup phase can retire suspended accounts without breaking opening-balance migration
67500 | User Story | Block manual general journal posting to sub-ledger control accounts | As a financial controller, I need to configure bank and other sub-ledger control main accounts to disallow manual general journal entry, so that postings flow through the appropriate sub-ledger modules and reconcile cleanly to GL. | [9 empty] | - Selected bank and sub-ledger main accounts have Do not allow manual entry enabled - Users post bank activity through cash and bank transactions that update the sub-ledger and GL automatically - Attempting to use a blocked account on a general journal is rejected with a clear validation message
67562 | User Story | Require approval before activating new main accounts | As a chief accountant, I need to require an approval-controlled process before a new main account is created or an existing Philips code is opened for Heartstream company codes, so that COA growth stays governed. | [9 empty] | - New main account requests require chief accountant (or delegate) approval before the account is active for posting - Opening an existing unused code from the parent chart follows the same approval path - Approved accounts are created in D365 with required type, category, and dimension rules applied
67507 | User Story | Require approval before activating new main accounts | As a chief accountant, I need to require an approval-controlled process before a new main account is created or an existing Philips code is opened for Heartstream company codes, so that COA growth stays governed. | [9 empty] | - New main account requests require chief accountant (or delegate) approval before the account is active for posting - Opening an existing unused code from the parent chart follows the same approval path - Approved accounts are created in D365 with required type, category, and dimension rules applied
67560 | User Story | Require approval before activating new main accounts | As a chief accountant, I need to require an approval-controlled process before a new main account is created or an existing Philips code is opened for Heartstream company codes, so that COA growth stays governed. | [9 empty] | - New main account requests require chief accountant (or delegate) approval before the account is active for posting - Opening an existing unused code from the parent chart follows the same approval path - Approved accounts are created in D365 with required type, category, and dimension rules applied
67489 | User Story | Omit main-account-level totaling on trial balance | As a financial controller, I need to run trial balance inquiry without main-account-level totaling lines, so that reviewers can validate double-entry balance without extra subtotal rows that caused confusion in legacy reporting. | [9 empty] | - Trial balance for main accounts does not insert asset/expense subtotal rows at individual account level - Financial statement and management reports still show section and hierarchy totals - Users can opt into D365 totaling features only if a future review finds them useful
67562 | User Story | Omit main-account-level totaling on trial balance | As a financial controller, I need to run trial balance inquiry without main-account-level totaling lines, so that reviewers can validate double-entry balance without extra subtotal rows that caused confusion in legacy reporting. | [9 empty] | - Trial balance for main accounts does not insert asset/expense subtotal rows at individual account level - Financial statement and management reports still show section and hierarchy totals - Users can opt into D365 totaling features only if a future review finds them useful
67514 | User Story | Configure business unit profit center and cost center dimensions | As a finance functional lead, I need to configure business unit, profit center, and cost center as financial dimensions in D365 Finance, so that operational postings match Heartstream management and consolidation hierarchies. | [9 empty] | - Financial dimensions exist for business unit, profit center, and cost center with values loaded from approved master data - Dimension values reflect global master data where standardized across legal entities - Legal-entity-specific cost center values are supported where R&D or other functions do not exist in all entities
67494 | User Story | Configure business unit profit center and cost center dimensions | As a finance functional lead, I need to configure business unit, profit center, and cost center as financial dimensions in D365 Finance, so that operational postings match Heartstream management and consolidation hierarchies. | [9 empty] | - Financial dimensions exist for business unit, profit center, and cost center with values loaded from approved master data - Dimension values reflect global master data where standardized across legal entities - Legal-entity-specific cost center values are supported where R&D or other functions do not exist in all entities
67491 | User Story | Configure business unit profit center and cost center dimensions | As a finance functional lead, I need to configure business unit, profit center, and cost center as financial dimensions in D365 Finance, so that operational postings match Heartstream management and consolidation hierarchies. | [9 empty] | - Financial dimensions exist for business unit, profit center, and cost center with values loaded from approved master data - Dimension values reflect global master data where standardized across legal entities - Legal-entity-specific cost center values are supported where R&D or other functions do not exist in all entities
67491 | User Story | Standardize cost center master data across legal entities | As a chief accountant, I need to manage cost centers with a standardized structure and nomenclature across legal entities where possible, so that authorization and maintenance are not duplicated company code by company code. | [9 empty] | - Shared cost center values use consistent numbering and naming across legal entities where the function exists - Cost centers that are legal-entity-specific remain restricted to that entity - Finance can maintain cost centers centrally rather than only through per-company-code matrices where D365 global dimension configuration allows
67564 | User Story | Standardize cost center master data across legal entities | As a chief accountant, I need to manage cost centers with a standardized structure and nomenclature across legal entities where possible, so that authorization and maintenance are not duplicated company code by company code. | [9 empty] | - Shared cost center values use consistent numbering and naming across legal entities where the function exists - Cost centers that are legal-entity-specific remain restricted to that entity - Finance can maintain cost centers centrally rather than only through per-company-code matrices where D365 global dimension configuration allows
67562 | User Story | Standardize cost center master data across legal entities | As a chief accountant, I need to manage cost centers with a standardized structure and nomenclature across legal entities where possible, so that authorization and maintenance are not duplicated company code by company code. | [9 empty] | - Shared cost center values use consistent numbering and naming across legal entities where the function exists - Cost centers that are legal-entity-specific remain restricted to that entity - Finance can maintain cost centers centrally rather than only through per-company-code matrices where D365 global dimension configuration allows
67511 | User Story | Represent functional area for consolidated P and L reporting | As a finance business partner, I need to represent functional area (manufacturing, selling, G&A, R&D) for reporting and posting control, either as a financial dimension or as a deterministic attribute of cost center, so that consolidated P&L views match Heartstream expectations. | [9 empty] | - Functional area is available on expense-related transactions for reporting consistent with cost center ranges (for example 1000 manufacturing, 2000 selling, 3000 G&A, 5000 R&D) - Design choice between separate dimension vs cost-center-derived mapping is documented (DQ-GL-002) - GL accounts that must not post to incompatible functional areas are enforceable through account structure rules
67507 | User Story | Enforce account structure rules for dimension combinations | As a financial controller, I need to configure account structure and advanced rules that restrict which financial dimension values can post to which main account ranges, so that users cannot book COGS to finance cost centers or violate similar policy rules. | [9 empty] | - Account structures cover active main account ranges with required dimension segments - Invalid dimension combinations are blocked at transaction entry - Advanced rules add conditional dimensions (for example worker on travel accounts) only where needed without adding global dimensions
67563 | User Story | Default profit center and cost center on SCM-driven transactions | As a finance operations lead, I need to default profit center and cost center on sales, purchase, and inventory transactions from product and site setup, so that material-level activity rolls up to the correct management hierarchy. | [9 empty] | - SCM integration can populate profit center on order and inventory transactions per agreed material and site mapping - Financial dimensions on sales order lines are defaulted or mandatory per configuration - Detailed material-to-profit-center mapping is confirmed with SCM workstream (DQ-GL-008)
67490 | User Story | Default profit center and cost center on SCM-driven transactions | As a finance operations lead, I need to default profit center and cost center on sales, purchase, and inventory transactions from product and site setup, so that material-level activity rolls up to the correct management hierarchy. | [9 empty] | - SCM integration can populate profit center on order and inventory transactions per agreed material and site mapping - Financial dimensions on sales order lines are defaulted or mandatory per configuration - Detailed material-to-profit-center mapping is confirmed with SCM workstream (DQ-GL-008)
67665 | User Story | Default profit center and cost center on SCM-driven transactions | As a finance operations lead, I need to default profit center and cost center on sales, purchase, and inventory transactions from product and site setup, so that material-level activity rolls up to the correct management hierarchy. | [9 empty] | - SCM integration can populate profit center on order and inventory transactions per agreed material and site mapping - Financial dimensions on sales order lines are defaulted or mandatory per configuration - Detailed material-to-profit-center mapping is confirmed with SCM workstream (DQ-GL-008)
67509 | User Story | Limit active financial dimensions for performance | As a solution architect, I need to limit the implemented set of active financial dimensions to a small approved list (target approximately four to five), so that transaction entry and reporting performance remain acceptable. | [9 empty] | - Approved dimension list for phase 1 is documented and excludes optional dimensions unless justified - Additional reporting attributes use financial tags or BI where they are not needed on trial balance - Dimension count review is part of solution sign-off before UAT
67506 | User Story | Limit active financial dimensions for performance | As a solution architect, I need to limit the implemented set of active financial dimensions to a small approved list (target approximately four to five), so that transaction entry and reporting performance remain acceptable. | [9 empty] | - Approved dimension list for phase 1 is documented and excludes optional dimensions unless justified - Additional reporting attributes use financial tags or BI where they are not needed on trial balance - Dimension count review is part of solution sign-off before UAT
67520 | User Story | Limit active financial dimensions for performance | As a solution architect, I need to limit the implemented set of active financial dimensions to a small approved list (target approximately four to five), so that transaction entry and reporting performance remain acceptable. | [9 empty] | - Approved dimension list for phase 1 is documented and excludes optional dimensions unless justified - Additional reporting attributes use financial tags or BI where they are not needed on trial balance - Dimension count review is part of solution sign-off before UAT
| User Story | Align all legal entities to a single fiscal calendar at go-live | As a group controller, I need to align all Heartstream legal entities including India and Australia on one fiscal calendar with a December year-end before go-live, so that period close and consolidation timelines are aligned. | [9 empty] | - Fiscal calendar configuration uses one calendar for all in-scope legal entities at go-live - India completes transition from March year-end to December year-end before go-live as planned - Australia remains on December year-end aligned with the group
67658 | User Story | Allow controlled posting to prior periods after soft close | As a financial controller, I need to reopen prior fiscal periods in a controlled manner for correcting entries, so that month-end close discipline is maintained without permanent lock-out. | [9 empty] | - Closed periods use on-hold or equivalent soft-close status rather than permanent close by default - Only authorized users can reopen a prior period module or ledger for posting - Reopened period postings are auditable (user, date, period)
67676 | User Story | Allow controlled posting to prior periods after soft close | As a financial controller, I need to reopen prior fiscal periods in a controlled manner for correcting entries, so that month-end close discipline is maintained without permanent lock-out. | [9 empty] | - Closed periods use on-hold or equivalent soft-close status rather than permanent close by default - Only authorized users can reopen a prior period module or ledger for posting - Reopened period postings are auditable (user, date, period)
67667 | User Story | Allow controlled posting to prior periods after soft close | As a financial controller, I need to reopen prior fiscal periods in a controlled manner for correcting entries, so that month-end close discipline is maintained without permanent lock-out. | [9 empty] | - Closed periods use on-hold or equivalent soft-close status rather than permanent close by default - Only authorized users can reopen a prior period module or ledger for posting - Reopened period postings are auditable (user, date, period)
67658 | User Story | Close AR and AP modules before general ledger period | As a financial controller, I need to configure ledger calendar status to close customer and vendor sub-ledgers while GL remains open for adjustments, so that sub-ledger close on working day 2 and GL close on working day 4 can be enforced. | [9 empty] | - Ledger calendar supports module-level period status per legal entity - AR and AP modules can be set on hold while GL remains open for the same period - Posting to closed AR or AP modules is blocked for users without override access
67667 | User Story | Close AR and AP modules before general ledger period | As a financial controller, I need to configure ledger calendar status to close customer and vendor sub-ledgers while GL remains open for adjustments, so that sub-ledger close on working day 2 and GL close on working day 4 can be enforced. | [9 empty] | - Ledger calendar supports module-level period status per legal entity - AR and AP modules can be set on hold while GL remains open for the same period - Posting to closed AR or AP modules is blocked for users without override access
67500 | User Story | Close AR and AP modules before general ledger period | As a financial controller, I need to configure ledger calendar status to close customer and vendor sub-ledgers while GL remains open for adjustments, so that sub-ledger close on working day 2 and GL close on working day 4 can be enforced. | [9 empty] | - Ledger calendar supports module-level period status per legal entity - AR and AP modules can be set on hold while GL remains open for the same period - Posting to closed AR or AP modules is blocked for users without override access
67610 | User Story | Maintain monthly exchange rates shared across company codes | As a treasury lead, I need to maintain exchange rates updated monthly and available to all company codes that share rate types, so that revaluation and translation use consistent rates group-wide. | [9 empty] | - Exchange rate types required for Heartstream (including legacy actuals types) are configured - Monthly rates can be entered or imported once and consumed by all relevant legal entities - Decision on automated Oanda or other provider integration is recorded (DQ-GL-004)
| User Story | Run foreign currency revaluation across GL and sub-ledgers | As a financial controller, I need to run foreign currency revaluation processes for GL, AR, AP, and bank balances, so that month-end balances reflect closing rates in our multi-currency environment. | [9 empty] | - GL revaluation can be simulated and posted for balance sheet and income statement accounts as configured - AR, AP, and bank foreign currency revaluation routines are executable per legal entity - Revaluation postings can be reversed when required
67643 | User Story | Track month-end close tasks in period close workspace | As a financial controller, I need to track month-end close checklist activities in D365 period close workspace (sub-ledger close, recurring accruals, reconciliations, forex routines), so that the lean finance team can see status across company codes. | [9 empty] | - Period close workspace lists tasks aligned to Heartstream month-end checklist categories - Tasks can be assigned and marked complete per legal entity and period - Manual recurring accrual journals remain supported until accrual automation is defined (DQ-GL-005)
67658 | User Story | Track month-end close tasks in period close workspace | As a financial controller, I need to track month-end close checklist activities in D365 period close workspace (sub-ledger close, recurring accruals, reconciliations, forex routines), so that the lean finance team can see status across company codes. | [9 empty] | - Period close workspace lists tasks aligned to Heartstream month-end checklist categories - Tasks can be assigned and marked complete per legal entity and period - Manual recurring accrual journals remain supported until accrual automation is defined (DQ-GL-005)
67667 | User Story | Track month-end close tasks in period close workspace | As a financial controller, I need to track month-end close checklist activities in D365 period close workspace (sub-ledger close, recurring accruals, reconciliations, forex routines), so that the lean finance team can see status across company codes. | [9 empty] | - Period close workspace lists tasks aligned to Heartstream month-end checklist categories - Tasks can be assigned and marked complete per legal entity and period - Manual recurring accrual journals remain supported until accrual automation is defined (DQ-GL-005)
67525 | User Story | Configure segregation of duties through security roles | As a chief accountant, I need to configure D365 Finance security roles so invoice processing, payment processing, and GL posting can be separated by user despite a small finance team, so that internal control expectations are met. | [9 empty] | - Security roles are assigned per user with documented SoD intent (for example AP entry vs payment vs GL) - Users without role access cannot reach restricted workspaces or journals - Role design is validated in UAT with named finance team members
67502 | User Story | Configure segregation of duties through security roles | As a chief accountant, I need to configure D365 Finance security roles so invoice processing, payment processing, and GL posting can be separated by user despite a small finance team, so that internal control expectations are met. | [9 empty] | - Security roles are assigned per user with documented SoD intent (for example AP entry vs payment vs GL) - Users without role access cannot reach restricted workspaces or journals - Role design is validated in UAT with named finance team members
| User Story | Use identifiable voucher number sequences for intercompany journals | As a financial controller, I need to assign a dedicated number sequence prefix to intercompany general journals, so that intercompany vouchers are easy to identify in GL inquiry and reconciliation. | [9 empty] | - Intercompany journal name uses a dedicated number sequence (for example Interco prefix) - Posted intercompany vouchers display the configured prefix - Number sequences are consistent across legal entities that use the shared intercompany journal setup
67525 | User Story | Print customer invoices in local language per customer | As a regional finance user, I need to print customer invoice documents in the customer's required local language (for example China or Japan), so that statutory and customer-facing documents are acceptable in each market. | [9 empty] | - Customer master supports a document language preference independent of company default language - Customer invoices render in the language defined on the customer when local language is required - Legal-entity language still drives localization features such as tax statements per country
67502 | User Story | Print customer invoices in local language per customer | As a regional finance user, I need to print customer invoice documents in the customer's required local language (for example China or Japan), so that statutory and customer-facing documents are acceptable in each market. | [9 empty] | - Customer master supports a document language preference independent of company default language - Customer invoices render in the language defined on the customer when local language is required - Legal-entity language still drives localization features such as tax statements per country
67482 | User Story | Print customer invoices in local language per customer | As a regional finance user, I need to print customer invoice documents in the customer's required local language (for example China or Japan), so that statutory and customer-facing documents are acceptable in each market. | [9 empty] | - Customer master supports a document language preference independent of company default language - Customer invoices render in the language defined on the customer when local language is required - Legal-entity language still drives localization features such as tax statements per country
| Task | Provide revised BU MRU and profit center hierarchy to implementation team |  | Workshop Action item | [6 empty] | Day 2\Business E2E flow
| Task | Share sample management and consolidation reports for dimension mapping |  | Workshop Action item | [6 empty] | Day 2\Business E2E flow
| Issue | Accrual deferral and ledger allocation workshop incomplete | Risk: Accrual/deferral management and ledger allocation demonstrations were deferred; requirements were not finalized in this session. Impact: Automated accrual/deferral and allocation user stories cannot be baselined until the follow-up workshop completes. Mitigation: Schedule residual agenda (target Wednesday follow-up per facilitators); register DQ-GL-005. | [7 empty] | Day 2\Business E2E flow
| Risk | Finance GL features missing from ADO feature catalog | Risk: Generated GL user stories cannot be linked to catalog Feature work items because feature.json contains no GL-specific Feature titles. Impact: ADO import will have blank Feature IDs until catalog Features are authored for WS-02 GL scope. Mitigation: Add Epic/Feature hierarchy for Record-to-Report GL in ADO and re-run work-item mapping. | [7 empty] | Day 2\Business E2E flow